## Slide 1: Chapter 15, Software Life Cycle

## Slide 2: Lecture Road Map
Software Development as Application Domain
  Modeling the software lifecycle
IEEE Standard 1074 for Software Lifecycles
Modeling the software life cycle
  Sequential models
    Pure waterfall model
    V-model
  Iterative models
    Boehm’s spiral model
    Unified Process (in the next lecture)
  Entity-oriented models
    Issue-based model
Capability Maturity Model
Notes:   Waterfall model and its problems
    Pure Waterfall Model
    V-Model
    Sawtooth Model
  Alternative process models
    Boehm’s Spiral Model
    Issue-based Development Model

## Slide 3: Inherent Problems with Software Development
Requirements are constantly changing
  The client might not know all the requirements in advance
Frequent changes are difficult to manage
  Identifying checkpoints for planning and cost estimation is difficult
There is more than one software system
  New system must often be backward compatible with existing system (“legacy system”)
Notes: Requirements are constantly changing
  The client might not know all the requirements in advance
  Technology enablers offer new possibilities
Frequent changes are difficult to manage
  Identifying checkpoints for planning and cost estimation is difficult
There is more than one software system
  New system must often be backward compatible with existing system (“legacy system”)
  Phased development: The organization distinguishes between a system under development and the already released systems
Let’s view these problems as the nonfunctional requirements for a system that supports software development! (CASE = Computer Aided Software Engeering)
This leads us to software life cycle modeling

## Slide 4: Software Life Cycle
The term “Lifecycle” is based on the metaphor of the life of a person:
Post- Development
Conception
Development
Pre- Development
Childhood
Adulthood
Retirement
Childhood

## Slide 5: Typical Software Life Cycle Questions
Which activities should we select for the software project?
What are the dependencies between activities?
How should we schedule the activities?
To find these activities and dependencies we can use the same modeling techniques we use for software development:
  Functional Modeling of a Software Lifecycle
    Scenarios
    Use case model
  Structural modeling of a Software Lifecycle
    Object identification
    Class diagrams
  Dynamic Modeling of a Software Lifecycle
    Sequence diagrams, statechart and activity diagrams

## Slide 6: Identifying Software Development Activities
Questions to ask:
  What is the problem?
  What is the solution?
  What are the best mechanisms to implement the solution?
  How is the solution constructed?
  Is the problem solved?
  Can the customer use the solution?
  How do we deal with changes that occur during the development? Are enhancements needed?

## Slide 7: Software Development Activities (Example 1)
Requirements Analysis
System Design
What is the problem?
What is the solution?
Detailed Design
What are the best mechanisms
Program Implementation
How is the solution
constructed?
Testing
Is the problem solved?
Delivery
Can the customer use the solution?
Maintenance
Are enhancements needed?
to implement the solution?
Application
Domain
Solution
Domain

## Slide 8: Software Development Activities (Example 2)
Requirements Analysis
System Design
What is the problem?
What is the solution?
Object Design
What are the best mechanisms
to implement the solution?
Implementation
How is the solution
constructed?
Application
Domain
Solution
Domain

## Slide 9: Definitions
Software life cycle:
  Set of activities and their relationships to each other to support the development of a software system
Software development methodology:
  A collection of techniques for building models applied across the software life cycle
Notes: Development activities deal with the complexity by constructing and validating models of the application domain or the system. Development activities include:
requirements elicitation, analysis, system design, object design. Implementation,. testing
The associated figure depicts an overview of the relationship among these activities and their products.
A methodology is a collection of methods for solving a class of problems and specifies how and when each method should be used.
A seafood cookbook with a collection of recipes is a methodology for preparing seafood if it also contains advice on how ingredients should be used and what to do if not all ingredients are always available. Royce’s methodology [Royce, 1998], the Object Modeling Technique (OMT [Rumbaugh et al., 1991]), the Booch methodology [Booch, 1994], and Catalysis [D’Souza & Wills, 1999], are object-oriented methodologies for developing software.

## Slide 10: Functional Model of a simple life cycle model
Developer
Client
Project manager
System development
Problem definition
<<include>>
<<include>>
<<include>>
Software development
System operation
End user
Administrator
Notes: So far we used UML as a modeling language for describing and communicating about systems. In this chapter, we focus on models of the software development process, called software life cycle models.
Modeling the software life cycle is a difficult undertaking, because it is a complex and changing system. As software systems, software life cycles can be described by several different models.
Most proposed life cycle models have focused on the activities of software development and represented them explicitly as first class objects. This view of the software life cycle is called activity centered.
An alternative view of the software life cycle is to focus on the work products created by these activities. This alternate view is called entity centered. The activity-centered view leads participants to focus on how work products are created.
The entity-centered view leads participants to focus on the content and structure of the work products. This slide shows a simple life cycle for software development using three activities: Problem definition, System development, and System operation.

## Slide 11: Activity Diagram for the same Life Cycle Model
Software development goes through a linear progression of states
called software development activities
Notes: This slide shows an activity-centered view of this simplistic life cycle model.
The associations between the activities show a linear time dependency, which is implied by the use of the activity diagram notation: The problem statement precedes system development, which in turn precedes system operation. Alternate time dependencies are possible

## Slide 12: Another simple Life Cycle Model
System Development and Market creation can be done in parallel.
They must be done before the system upgrade activity
System
upgrade
activity
Market
creation
activity
System
development
activity
Notes: For example, in the software life cycle shown in this slide, the activities System development and Market creation can be done concurrently

## Slide 13: Two Major Views of the Software Life Cycle
Activity-oriented view of a software life cycle
  Software development consists of a set of development activities
  all the examples so far
Entity-oriented view of a software life cycle
  Software development consists of the creation of a set of deliverables.

## Slide 14: Entity-centered view of Software Development
Software development consists of the creation of a
set of deliverables
Notes: This slide shows an entity centered view of the model shown in the previous slides.
Software development produces four entities, a Market survey document, a Requirements specification document, an Executable system and a Lessons learned document

## Slide 15: Combining Activities and Entities in One View
Notes: The activity-centered view and the entity-centered view are complementary, as illustrated in this slide.
For every product there is one or more activity that generates it.
The Problem definition activity uses a Market survey document as input and generates a Requirements specification document.
The System development activity takes the Requirements specification document as input and produces an Executable system.
System operation generates a Lessons learned document that could be used during the development of the next product.
Alternatively, every activity generates one or more products.

## Slide 16: IEEE Std 1074: Standard for Software Life Cycle Activities
IEEE Std 1074
Project
Management
Pre-
Development
Develop-
ment
Post-
Development
Cross-
Development
(Integral Processes)
> Project Initiation
>Project Monitoring
&Control
> Software Quality
Management
> Concept
Exploration
> System
Allocation
> Requirements
> Design
> Implemen-
tation
> Installation
> Operation &
Support
> Maintenance
> Retirement
> V & V
> Configuration
Management
> Documen-
tation
> Training
Process Group
Process
Notes: The life cycle activities are defined by the IEEE 1074 standard [IEEE Std. 1074-1997].
This standard introduces precise definitions that enable project participants to understand and communicate effectively about the life cycle..
The goal of the standard is to establish a common framework for developing life cycle models and provide examples for typical situations. The main activities introduced by the standard can be described by using UML diagrams.
A process is a set of activities that is performed towards a specific purpose (e.g., requirements, management, delivery). The IEEE standard lists a total of 17 processes. The processes are grouped into higher levels of abstractions called process groups.
Examples of process groups are project management, pre-development, development, and post-development. Examples of processes in the development process group include:
the Requirements Process, during which the developers develop the system models
the Design Process, during which developers decompose the system into components
the Implementation Process, during which developers realize each componen
From the developers’ point of view, the first processes (i.e., the Project Management Processes, and the Predevelopment Processes) have often already been initiated before their involvement with the project.

## Slide 17: Processes, Activities and Tasks
Process Group: Consists of a set of processes
Process: Consists of activities
Activity: Consists of sub activities and tasks
Process
Group
Process
Activity
Development
Design
Task
Design
Database
Make a
Purchase
Recommendation
Notes: Each process is composed of activities. An activity is a task or group of sub activities that are assigned to a team or a project participant to achieve a specific purpose.
The Requirements Process, for example, is composed of three activities:
Define and Develop Software Requirements, during which the functionality of the system is defined precisely
Define Interface Requirements, during which the interactions between the system and the user are precisely defined
Prioritize and Integrate Software Requirements, during which all requirements are integrated for consistency, and prioritized by client preference
The slide shows that “Make a Purchase Recommendation” is a task of the activity “Design Database”, which is part of the Design Process, which in turn is part of the process group Development.

## Slide 18: Object Model of the IEEE 1074 Standard
Process Group
Activity
Work Product
Resource
Task
Process
Money
Time
Participant
consumed by
produces
Work Unit
*
*
*
*
Software Life Cycle
*
*
Notes: Model of the software life cycle (UML class diagram).
A software life cycle consists of process groups, which in turn consist of processes.
A process accomplishes a specific purpose (e.g., requirements, design, installation).
A process consists of activities, which are in turn consists of sub-activities or tasks.
Tasks represent the smallest piece of work that is relevant to management.
Tasks consume resources and produces one or more work products. A project is an instance of a software life cycle
During planning, activities are decomposed into project specific tasks, are given a start and ending date
and assigned to a team or a project participant
During the project, actual work is tracked against planned tasks, and resources are reallocated to respond to problems

## Slide 19: Process Maturity
A software development process is mature
  if the development activities are well defined and
  if management has some control over the quality, budget and schedule of the project
Process maturity is described with
  a set of maturity levels and
  the associated measurements (metrics) to manage the process
Assumption:
  With increasing maturity the risk of project failure decreases
CMM: Capability Maturity Model (SEI,Humphrey)
Notes: Process maturity describes a set of maturity levels at which an organizations' development process takes place. Onle when the development process possesses sufficient structure and procedures does it make sense to collect certain kind of metrics.
Why do we care about process maturity? Well, with increasing maturity we assume that the risk of project failure decreases.
There is another implicit assumption here. This one says, that if you can decompose a process into a set of development activities, you actually can handle it better. This is not necessarily true. Good examples: Mozart. We don’t know how he composed, he might not have known it himself, at least he never wrote about it. And he composed wonderful music. One of the characteristics of his person is that he was able to keep a full score in his head before writing down the final composition. There are scores written by Mozart one hour before the performance with no writing mistakes. (The fact that they were written hourse before the performance was deduced from the haste the inkblotter was pushed on the notes to dry the ink.
Mozart was able to go to a church, hear a wonderful piece of music, with a duration of half an hour, then go home and write down the exact piece of music, all voices, from memory!

## Slide 20: CMM levels
1. Initial Level
  also called ad hoc or chaotic
2. Repeatable Level
  Process depends on individuals ("champions")
3. Defined Level
  Process is institutionalized (sanctioned by management)
4. Managed Level
  Activities are measured and provide feedback for resource allocation (process itself does not change)
5. Optimizing Level
  Process allows feedback of information to change process itself
Notes: CMM does not specify any particular process model.
But it does dictate guidance on how to measure the maturity of your process, as well as outline certain Key Process Areas (KPAs) that it deems necessary for achieving different maturity levels.

## Slide 21: What does Process Maturity Measure?
The real indicator of process maturity is the level of predictability of project performance (quality, cost, schedule).
Level 1: Random, unpredictable performance
Level 2: Repeatable performance from project to project
Level 3: Better performance on each successive project
Level 4: Substantial improvement (order of magnitude) in one dimension of project performance
Level 5: Substantial improvements across all dimensions of project performance.
Notes: Level 4 either
    Substantially (order of magnitude) in one dimension of project performance OR
    Significant in each dimension of project performance

## Slide 22: Key Process Areas
To achieve a specific level of maturity, the organization must demonstrate that it addresses all the key process areas defined for that level.
There are no key process areas for Level 1
KPA Level 2: Basic software project management practice
KPA Level 3: Infrastructure for single software life cycle model
KPA Level 4: Quantitative understanding of process and deliverables
KPA Level 5: Keep track of technology and process changes
Notes: To be able to measure the maturity of an organization,
a set of key process areas (KPA) has been defined by the SEI.
To achieve a specific level of maturity, the organization must demonstrate that it addresses all the key process areas defined for that level.
Some of these key process areas go beyond activities defined in the IEEE 1074 standard. The following slides show a mapping between maturity level and key process area
Focus of level 2 KPAs: Establish basic project management controls.
Focus of level 3 KPAs: Establish an infrastructure that allows a single effective software life cycle model across all projects.
Level 4 KPAs: Quantitative understanding of the software life cycle process and deliverables.
Level 5 KPAs: Focus: Keep track of technology and process changes that may cause change in the system model or deliverables even during the duration of a project.

## Slide 23: Pros and Cons of Process Maturity
Benefits:
  Increased control of projects
  Predictability of project cost and schedule
  Objective evaluations of changes in techniques, tools and methodologies
  Predictability of the effect of a change on project cost or schedule
Problems:
  Need to watch a lot (“Big brother“, „big sister“)
  Overhead to capture, store and analyse the required information
Agile Methodologies
  Deemphasize the importance of process maturity
    => Lecture on Methodologies
Notes: From Brian Noyes, http://www.fawcette.com/resources/managingdev/methodologies/cmm/default_pf.asp
The downside to CMM is that it requires a heavyweight process to meet all the guidelines for each KPA and produce all the associated artifacts necessary to get certified at a certain process maturity level. Also, interpreting specifically what you need to do or have in place to get certified at a given level can be vague and difficult.
But CMM is well recognized in the industry as a well-established measurement of process maturity, and you can find an immense amount of information through SEI's Web site and numerous books on the subject (see Resources).
In fact, a whole cottage industry has cropped up around CMM, with consultants and trainers who can help your company along the path to maturity if you can afford it. Many would argue that you can't afford to pass up the opportunity because, in the long run, achieving process maturity should save you money.
But the cost of getting there, especially with outside assistance, is significant and takes real commitment from management and the development team.

## Slide 24: Lecture Road Map
Software Development as Application Domain
  Modeling the software lifecycle
IEEE Standard 1074 for Software Lifecycles
Modeling the software life cycle
  Sequential models
    Pure waterfall model
    V-model
  Iterative models
    Boehm’s spiral model (Unified Process in the next lecture)
  Entity-oriented models
    Issue-based model
Capability Maturity Model
Notes: Many models have been proposed to deal with the problems of defining activities and associating them with each other
The first model proposed was the waterfall model [Royce]
Spiral model [Boehm]
Objectory process [Jacobsen]
Rational process [Kruchten]
Unified process [Jacobsen, Booch, Rumbaugh]
  Waterfall model and its problems
    Pure Waterfall Model
    V-Model
    Sawtooth Model
  Alternative process models
    Boehm’s Spiral Model
    Issue-based Development Model

## Slide 25: The Waterfall Model of the Software Life Cycle
Requirements
Process
System
Allocation
Process
Concept
Exploration
Process
Design
Process
Implementation
Process
Installation
Process
Operation &
Support Process
Verification
& Validation
Process
adapted from [Royce 1970]
Notes: The waterfall model was first described by Royse [Royce, 1970].
The waterfall model is an activity-centered life cycle model that prescribes a sequential execution of a subset of the development processes and management processes we have mentioned so far.
This slide shows UML activity diagram of the waterfall model adapted from [Royce, 1970] using IEEE 1074 names; project management and cross-development processes are omitted.
The requirements activities are all completed before the system design activity starts.
The goal is to never turn back once an activity is completed. The key feature of his model is the constant verification activity (called “verification step” by Royse) that ensures that each development activity does not introduce unwanted or deletes mandatory requirements.
This model provides a simple (or even simplistic) view of software development that measures progress by the number of tasks that have been completed.
The model assumes that software development can be scheduled as a step-by-step process that transforms user needs into code

## Slide 26: Example of a waterfall model : DOD Standard 2167A
Software development activities:
  System Requirements Analysis/Design
  Software Requirements Analysis
  Preliminary Design and Detailed Design
  Coding and CSU testing
  CSC Integration and Testing
  CSCI Testing
  System integration and Testing
Required by the U.S. Department of Defense for all software contractors in the 1980-90’s.
Notes: Waterfall-based software life cycle models are still widely used.
Up into the 1990s, software companies contracted by the US Department of Defense, for example, were required to use the 2167A standard [DoD-STD-2167A] which was based on the waterfall model.
  Coding and CSU testing (CSU = Computer Software Unit)
  CSC Integration and Testing (CSC = Computer Software Component, can be decomposed into CSC's and CSU's)
  CSCI Testing (CSCI = Computer Software Configuration Item)

## Slide 27: Activity Diagram of MIL DOD-STD-2167A
Preliminary
Design Review
Critical Design
Review (CDR)
System
Requirements
Review
System
Design
Review
Software
Specification
Review
System
Requirements
Analysis
Software
Requirements
Analysis
System
Design
…
Preliminary
Design
Detailed
Design
Coding &
CSU Testing
CSC
Integration
& Testing
Notes: The diamond below each activity denotes a decision point: The next activity is initiated
only if the review
is successful

## Slide 28: From the Waterfall Model to the V Model
System Design
Requirements
Analysis
Requirements
Engineering
Object Design
Integration Testing
System
Testing
Unit
Testing
Implemen-
tation
System
Testing
Unit
Testing
Integration
Testing
Acceptance
Notes: The V-model is a variation of the waterfall model that makes explicit the dependency between development activities and verification activities.
The difference between the waterfall model and the V model is that the latter makes explicit the notion of level of abstraction.
All activities from requirements to implementation focus on building more and more detailed representation of the system, whereas all activities from implementation to operation focus on validating the system. This slide shows origin of the V-model form the waterfall model.

## Slide 29: Activity Diagram of the V Model
Problem with the V-Model:
Developers Perception =
User Perception
precedes
Is validated by
Notes: This model is a UML activity diagram of the V-Model (adapted from [Jensen & Tonies, 1979]). It shows 2 types of dependencies: Precedes (which is a temporal dependency) and “is validated by” which shows
The horizontal object flow denotes the information flow between activities of same abstraction level. The V-shape layout of the activities was conserved to reflect the original drawing. However, the layout of the activities has no semantics in UML.
Higher levels of abstractions of the V-model deal with the requirements in terms of elicitation and operation. The middle-part of the V-model focuses on mapping the understanding of the problem into a software architecture. The lower level of the V-model focuses on details such as the assembly of software components and the coding of new ones.
For example, the goal of the Unit Test activity is to validate units against their description in the detailed design. The Component Integration and Test activity validates functional components against the preliminary (or high-level) design. In many aspects, the waterfall model and its variants are simplistic abstractions of the software development process.
The V-model, for example, does not distinguish between the developers and the users perception. It basically asks the user to follow the developer all the way into the abyss of detailed design and implementation! One attempt, to deal with the different levels of abstraction was the Sawtooth Model.

## Slide 30: Properties of Waterfall-based Models
Managers love waterfall models
  Nice milestones
  No need to look back (linear system)
  Always one activity at a time
  Easy to check progress during development: 90% coded, 20% tested
However, software development is non-linear
  While a design is being developed, problems with requirements are identified
  While a program is being coded, design and requirement problems are found
  While a program is tested, coding errors, design errors and requirement errors are found.
Notes: In practice, software development is not sequential
  The development stages overlap
The tendency to freeze parts of the development leads to systems the client does not want and which are badly structured as design problems are circumvented by tricky coding

## Slide 31: The Alternative: Allow Iteration
Escher was the first:-)
http://en.wikipedia.org/wiki/File:Escher_Waterfall.jpg
Note: The image is copyrighted
Notes: This beautiful drawing from Escher shows how difficult it is to allow iteration in a waterdall model without alluding to illusion!
Can this be built? Yes, no? Yes, it was built by a japanese artist with the name of
A different approach was needed. This leads us to the iterative models.

## Slide 32: Construction of Escher’s Waterfall Model
http://www.cs.technion.ac.il/~gershon/EscherForReal/EscherWaterfall2Penrose.gif
Note: The image is copyrighted
Notes: Here is our physical realization of Escher's Waterfall. You can also watch this object rotating in space in this avi movie. This realization stems from using three joint Penrose triangles along the water stream.
Note also the way the house is warped so as to look natural from this viewing direction (only)

## Slide 33: Spiral Model
The spiral model proposed by Boehm has the following set of activities
  Determine objectives and constraints
  Evaluate alternatives
  Identify risks
  Resolve risks by assigning priorities to risks
  Develop a series of prototypes for the identified risks starting with the highest risk
  Use a waterfall model for each prototype development
  If a risk has successfully been resolved, evaluate the results of the round and plan the next round
  If a certain risk cannot be resolved, terminate the project immediately
This set of activities is applied to a couple of so-called rounds.
Notes: Boehm’s spiral model [Boehm, 1987] is an activity-centered life cycle model that was devised to address the source of weaknesses in the waterfall model, in particular, to accommodate infrequent change during the software development. It based on the same activities as the waterfall model, however, it adds several activities such as risk management, reuse, and prototyping to each activity.
These extended activities are called cycles or rounds.
18

## Slide 34: Rounds in Boehm’s Spiral Model
Concept of Operations
Software Requirements
Software Product Design
Detailed Design
Code
Unit Test
Integration and Test
Acceptance Test
Implementation
For each round go through these activities:
  Define objectives, alternatives, constraints
  Evaluate alternatives, identify and resolve risks
  Develop and verify a prototype
  Plan the next round.
Notes: Each round follows the waterfall model and includes the following activities:
Determine objectives
Specify constraints
Generate alternatives
Identify risks
Resolve risks

## Slide 35: Diagram of Boehm’s Spiral Model
Notes: The spiral model focuses on addressing risks incrementally, in order of priority.
Boehm’s spiral model distinguishes the following rounds: Concept of Operation, Software Requirements, Software Product Design, Detailed Design, Code, Unit Test, Integration and Test, Acceptance Test, Implementation
Each round is composed of four phases.
The first 3 rounds are shown in a polar coordinate system.
  The polar coordinates r = (l, a) of a point indicate the resource spent in the project and the type of activity

## Slide 36: Round 1, Concept of Operations, Quadrant IV: Determine Objectives,Alternatives & Constraints
Project
Start
Notes: During the first phase (upper left quadrant), developers explore alternatives, define constraints, and identify objectives.

## Slide 37: Round 1, Concept of Operations, Quadrant I: Evaluate Alternatives, identify & resolve Risks
Risk Analysis
Notes: During the second phase (upper right quadrant), developers manage risks associated with the solutions defined during the first phase and specify a prototype to be built in the next phase

## Slide 38: Round 1, Concept of Operations, Quadrant II: Develop and Verify
Concept of Operation
Activity
Notes: During the third phase (lower right quadrant), developers realize and validate a prototype or the part of the system associated with the risks addressed in this round.

## Slide 39: Round 1, Concept of Operations, Quadrant III: Prepare for Next Activity
Requirements and
Life cycle Planning
Notes: The fourth phase (lower left quadrant) focuses on the planning of the next round based on the results produced in the current round.

## Slide 40: Round 2, Software Requirements, Quadrant IV: Determine Objectives,Alternatives & Constraints
Start
of Round 2
Notes: The last phase of the round is usually conducted as a review involving the project participants, including developers, clients, and users. This review covers the artifacts developed during the previous and current rounds and the plans for the next round.

## Slide 41: Comparison of Projects
Project P1
Project P2
Notes: To summaryize, The spiral model focuses on addressing risks incrementally, in order of priority.
Boehm’s spiral model distinguishes the following rounds: Concept of Operation, Software Requirements, Software Product Design, Detailed Design, Code, Unit Test, Integration and Test, Acceptance Test, Implementation
Each round is composed of four phases.
The first 3 rounds are shown in a polar coordinate system.
  The polar coordinates r = (l, a) of a point indicate the resource spent in the project and the type of activity
  The size of the arrow indicates the type of current activity in of the project (where are we?) as well as the resources spent in theproject (how much money did we spend so far?), which would allow a comparision of projects based on their location in the diagram. Project P1 is currently in risk analysis and has not spent as many resources as Project P2 which is currently developing and evaluating a prototype.

## Slide 42: Limitations of Waterfall and Spiral Models
Neither of these models deal well with frequent change
  The Waterfall model assumes that once you are done with a phase, all issues covered in that phase are closed and cannot be reopened
  The Spiral model can deal with change between phases, but does not allow change within a phase
What do you do if change is happening more frequently?
  “The only constant is the change”

## Slide 43: An Alternative: Issue-Based Development
A system is described as a collection of issues
  Issues are either closed or open
  Closed issues have a resolution
  Closed issues can be reopened (Iteration!)
The set of closed issues is the basis of the system model
I1:Open
I2:Closed
I3:Closed
A.I1:Open
A.I2:Open
SD.I1:Closed
SD.I2:Closed
SD.I3:Closed
Planning
Requirements Analysis
System Design

## Slide 44: Waterfall Model: Analysis Phase
I1:Open
I2:Open
I3:Open
A.I1:Open
A.I2:Open
SD.I1:Open
SD.I2:Open
SD.I3:Open
Analysis
Analysis

## Slide 45: Waterfall Model: Design Phase
I1:Closed
I2:Closed
I3:Open
A.I1:Open
A.I2:Open
SD.I1:Open
SD.I2:Open
SD.I3:Open
Analysis
Design
Analysis

## Slide 46: Waterfall Model: Implementation Phase
I1:Closed
I2:Closed
I3:Closed
A.I1:Closed
A.I2:Closed
SD.I1:Open
SD.I2:Open
SD.I3:Open
Implementation
Design
Analysis

## Slide 47: Waterfall Model: Project is Done
I1:Closed
I2:Closed
I3:Closed
A.I1:Closed
A.I2:Closed
SD.I1:Open
SD.I2:Open
SD.I3:Open
Implementation
Design
Analysis

## Slide 48: Issue-Based Model: Analysis Phase
I1:Open
I2:Open
I3:Open
D.I1:Open
Imp.I1:Open
Analysis:80%
Design: 10%
Implemen-tation: 10%

## Slide 49: Issue-Based Model: Design Phase
I1:Closed
I2:Closed
I3:Open
SD.I1:Open
SD.I2:Open
Imp.I1:Open
Imp.I2:Open
Imp.I3:Open
Analysis:40%
Design: 60%
Implemen-tation: 0%

## Slide 50: Issue-Based Model: Implementation Phase
I1:Open
I2:Closed
I3:Closed
A.I1:Open
A.I2:Closed
SD.I1:Open
SD.I2:Closed
SD.I3:Open
Analysis:10%
Design: 10%
Implemen-tation: 60%

## Slide 51: Issue-Based Model: Prototype is Done
I1:Closed
I2:Closed
I3: Pending
A.I1:Closed
A.I2:Closed
SD.I1:Open
SD.I2: Unresolved
SD.I3:Closed

## Slide 52: Frequency of Change and Choice of Software Lifecycle Model
  PT = Project Time, MTBC = Mean Time Between Change
  Change rarely occurs (MTBC » PT)
    Linear Model (Waterfall, V-Model)
    Open issues are closed before moving to next phase
  Change occurs sometimes (MTBC ≈ PT)
    Iterative model (Spiral Model, Unified Process)
    Change occurring during phase may lead to iteration of a previous phase or cancellation of the project
  Change is frequent (MTBC « PT)
    Issue-based Model (Concurrent Development, Scrum)
    Phases are never finished, they all run in parallel.

## Slide 53: Summary
Software life cycle models
  Sequential models
    Pure waterfall model and V-model
    Sawtooth model
  Iterative model
    Boehm’s spiral model
      Rounds
      Comparison of projects
  Prototyping
    Revolutionary and evolutionary prototyping
    Time-boxed prototyping instead of rapid prototyping
  Entity-oriented models
    Issue-based model
    Sequential models can be modeled as special cases of the issue-based model.

## Slide 54: Additional and Backup Slides

## Slide 55: Questions
Boehm‘s spiral model is usually shown in a polar coordinate system.
Why did Boehm use such a notation?
What are the problems with such a notation?
What happens if you attempt to remodel the spiral model in UML?

## Slide 56: Industry Distribution across Maturity Levels (State of the Software Industry in 1995)
Maturity Level Frequency
1 Initial 70%
2 Repeatable 15%
3 Defined < 10%
4 Managed < 5%
5 Optimizing < 1%
Source: Royce, Project Management, page 364
Citation needs to be updated

## Slide 57: Movie of Escher’s Waterfall Model
Escher for Real
http://www.cs.technion.ac.il/~gershon/EscherForRealWaterfallFull.avi
(C) Copyright 2002-5 Gershon Elber,Computer Science Department, Technion

## Slide 58: OOSE-Book: Development activities and their products
Requirements
elicitation
Analysis
System design
problem statement
functional model
nonfunctional requirements
object model
dynamic model
class diagram
use case diagram
statechart diagram
sequence diagram
Notes: The analysis Object model is often called briefly the object model, if the context specifies that it is the model created during analysis.

## Slide 59: OOSE- Development activities (cont’d)
System design
Object design
Implemen-tation
object design model
design goals
subsystem decomposition
source
code
Testing
deliverable system
class diagram

## Slide 60: Insert: Types of Prototypes
Illustrative Prototype
  Develop the user interface with a set of storyboards
  Implement them on a napkin or with a user interface builder (Visual C++, ....)
  Good for first dialog with client
Functional Prototype
  Implement and deliver an operational system with minimum functionality
  Then add more functionality
  Order identified by risk
Exploratory Prototype ("Hack")
  Implement part of the system to learn more about the requirements.
  Good for paradigm breaks

## Slide 61: Types of Prototyping
Revolutionary Prototyping
  Also called specification prototyping
  Get user experience with a throwaway version to get the requirements right, then build the whole system
    Advantage: Can be developed in a short amount of time.
    Disadvantage: Users may have to accept that features in the prototype are expensive to implement
Evolutionary Prototyping
  The prototype is used as the basis for the implementation of the final system
    Advantage: Short time to market
    Disadvantage: Can be used only if target system can be constructed in prototyping language
Notes: Another disadvantage of revolutionary prototyping:
User may be disappointed when some of the functionality and user interface evaporates because it can not be made available in the implementation environment

## Slide 62: Prototyping vs. Rapid Development
Revolutionary prototyping is sometimes called rapid prototyping
Rapid Prototyping is not a good term because it confuses prototyping with rapid development
  Prototyping is a technical issue: It is a particular model in the life cycle process
  Rapid development is a management issue. It is a particular way to control a project
Prototyping can go on forever if it is not restricted
    “Time-boxed” prototyping limits the duration of the prototype development

## Slide 63: References
Readings used for this lecture
  [Bruegge-Dutoit] Chapter 12
  [Humphrey 1989] Watts Humphrey, Managing the Software Process, SEI Series in Software Engineering, Addison Wesley, ISBN 0-201-18095-2
Additional References
  [Royce 1970] Winston Royce, Managing the Development of Large Software Systems, Proceedings of the IEEE WESCON, August 1970, pp. 1-9
  SEI Maturity Questionaire, Appendix E.3 in [Royce 1998], Walker Royce, Software Project Management, Addison-Wesley, ISBN0-201-30958-0

## Slide 64: Additional References
Overview of Capability Maturity Models
  http://www.sei.cmu.edu/cmm/cmms/cmms.html
Personal Process
  http://www.sei.cmu.edu/tsp/psp.html
Team Process:
  http://www.sei.cmu.edu/tsp/tsp.html
Notes: Because personnel costs constitute 70 percent of the cost of software development, the skills and work habits of engineers largely determine the results of the software development process.
Based on practices found in the Capability Maturity Model (CMM), the PSP can be used by engineers
as a guide to a disciplined and structured approach to developing software.
The PSP is a prerequisite for an organization planning to introduce the TSP.
The Team Software Process (TSP), along with the Personal Software Process, helps the high-performance engineer to･ensure quality software products･create secure software products･improve process management in an organizationEngineering groups use the TSP to apply integrated team concepts to the development of software-intensive systems.
A four-day launch process walks teams and their managers through･establishing goals･defining team roles･assessing risks･producing a team planAfter the launch, the TSP provides a defined process framework for managing, tracking and reporting the team's progress.
Using TSP, an organization can build self-directed teams that plan and track their work, establish goals, and own their processes and plans. These can be pure software teams or integrated product teams of 3 to 20 engineers

## Slide 65: Summary
Software life cycle
  The development process is broken into individual pieces called software development activities
Software development standards
  IEEE 1074
  The standard allows the lifecycle to be tailored
Capability Maturity Model
  An attempt to characterize the maturity of a software development organization following a software lifecycle model.
Notes: No good model for modeling the process (black art)
Several models have been proposed, linear and nonlinear models, which we will introduce
In the following lectures

## Slide 66: Maturity Level 1: Chaotic Process
Ad hoc approach to software development activities
No problem statement or requirements specification
Output is expected
  but nobody knows how to get there in a deterministic fashion
Similar projects may vary widely in productivity
  "when we did it last year we got it done"
Level 1 Metrics: Rate of Productivity (Baseline comparisons, Collection of data is difficult)
  Product size (LOC, number of functions, etc)
  Staff effort (“Man-years”, person-months)
Recommendation: Level 1 managers & developers should not concentrate on metrics and their meanings,
  They should first attempt to adopt a process model (waterfall, spiral model, saw-tooth, macro/micro process lifecycle, unified process)
Notes: In the next 5 slides, we view the process maturity in concert with the types of measurements needed to help us manage the process.
The first level of process is called initial or also chaotic. It is characterized by an ad hoc approach to the software development process. That is the inputs to the process are ill-defined, the outputs are expected, but nobody knows how to to do the transition from the non-existing or ill-defined inputs to the output

## Slide 67: Maturity Level 2: Repeatable Process
Inputs and outputs are defined
  Input: Problem statement or requirements specification
  Output: Source code
Process itself is a black box ( activities within process are not known)
  No intermediate products are visible
  No intermediate deliverables
Process is repeatable due to some individuals who know how to do it
  "Champion"
Level 2 Metrics:
  Software size: Lines of code, Function points, classes or method counts
  Personnel efforts: person-months
  Technical expertise
    Experience with application domain
    Design experience
    Tools & Method experience
  Employee turnover within project
Notes: What is the problem with indicating the success or status of a project by lines of code? Well, how about decreasing the code produced by the way of reuse or by inheritance?
How big is JEWEL?
How many person-months have been invested? 45 students * 3 months = 11 man-years.
Technical expertise of our class:
  No application domain experience
  No design experience
  No tool and no method experience
How many have dropped the class: 5 students in this semester

## Slide 68: Example: LOC (Lines of Code) Metrics
Numbers do not include:
> reused code
> classes from class libraries
Lines of Code
# of Classes
Lines of Code/Student
F'89
F'91
F'92
S'91
S'92
S'93
0
5000
10000
15000
20000
25000
30000
35000
40000
0
100
200
300
400
500
600
F'89
F'91
F'92
S'91
S'92
S'93
0
500
1000
1500
2000
2500
3000
F'89
F'91
F'92
S'91
S'92
S'93
Basic Course
Adv. Course
Notes: These are metrices used in 15-413 projects from Fall 89 (Workstation Fax) to Spring 93 (FRIEND). They show, in terms of lines of code, the growing complexity of the systems developed. The number of classes starts with 0 in Fall 89, we used functioal decomposition in that year and ends with 550 classes in Spring 93.
One observation we made was that on the average we can count on about 1000 lines of code per student per Fall semester. In the advanced course, we see this number doubling and tripling. In many cases, this can be contributed to the advanced knowledge but often also to the fact, that the most motivated students continued with the course, and now the average is no longer pulled down by people writing significantly less than 1000 lines.

## Slide 69: Maturity Level 3: Defined Process
Activities of software development process are well defined with clear entry and exit conditions.
Intermediate products of development are well defined and visible
Level 3 Metrics (in addition to metrics from lower maturity levels):
  Requirements complexity: Number of classes, methods, interfaces
  Design complexity: Number of subsystems, concurrency, platforms
  Implementation complexity: Number of code modules, code complexity
  Testing complexity: Number of paths to test, number of class interfaces to test
  Thoroughness of Testing:
    Requirements defects discovered
    Design defects discovered
    Code defects discovered
    Failure density per unit (subsystem, code module, class
Notes: When a process is well defined, we can assign metrics to each of the activities in that process. Objectory activites: Requirements analysis, design, coding
Requirements complexity: How many use cases?
Design complexity: How many subsystems?
Code complexity: how many classes?
Test complexity: How many unit tests, subsystem tests?
How many iterations?
How many defects (analysis, design, implementation) were discovered?

## Slide 70: Maturity Level 4: Managed Process
Uses information from early project activities to set priorities for later project activities (intra-project feedback)
  The feedback determines how and in what order resources are deployed
Effects of changes in one activity can be tracked in the others
Level 4 Metrics:
  Number of iterations per activity
  Code reuse: Amount of producer reuse (time designated for reuse for future projects?)
  Amount of component reuse (reuse of components from other projects and components)
  Defect identification:
    How and when (which review) are defects discovered?
  Defect density:
    When is testing complete?
  Configuration management:
    Is it used during the development process? (Has impact on tracability of changes).
  Module completion time:
    Rate at which modules are completed (Slow rate indicates that the process needs to be improved).
Notes: Defect discovery: Knowning whether defects are discovered during requirements reviews, design reviews or code walkthroughs determines the effectiveness of these activities
Even if iteration is employed, the basic activites themselves do not change

## Slide 71: Maturity Level 5: Optimizing Process
Measures from software development activities are used to change and improve the current process
This change can affect both the organization and the project:
  The organization might change its management scheme
  A project may change its process model before completion
Notes: Change in management scheme: From chief programmer team to egoless programming
Change in process: From SA/SD to OMT. Which company is doing this right now? None?
Is Level 5 achievable? Not clear!

## Slide 72: Determining the Maturity of a Project
Level 1 questions:
  Has a process model been adopted for the Project?
Level 2 questions:
  Software size: How big is the system?
  Personnel effort: How many person-months have been invested?
  Technical expertise of the personnel:
    What is the application domain experience
    What is their design experience
    Do they use tools?
    Do they have experience with a design method?
  What is the employee turnover?
Notes: Right now we ask these kind of questions with respect to JEWEL. Learn these questions and apply them to your next project (or ask them when you interview for a position)

## Slide 73: Maturity Level 3 Questions
What are the software development activities?
Requirements complexity:
  How many requirements are in the requirements specification?
Design complexity:
  Does the project use a software architecture? How many subsystems are defined? Are the subsystems tightly coupled?
Code complexity: How many classes are identified?
Test complexity:
  How many unit tests, subsystem tests need to be done?
Documentation complexity: Number of documents & pages
Quality of testing:
  Can defects be discovered during analysis, design, implementation? How is it determined that testing is complete?
  What was the failure density? (Failures discovered per unit size)

## Slide 74: Maturity Level 4 and 5 Questions
Level 4 questions:
  Has intra-project feedback been used?
  Is inter-project feedback used? Does the project have a post-mortem phase?
  How much code has been reused?
  Was the configuration management scheme followed?
  Were defect identification metrics used?
  Module completion rate: How many modules were completed in time?
  How many iterations were done per activity?
Level 5 questions:
  Did we use measures obtained during development to influence our design or implementation activities?
Notes: Intra-project feedback: yes, iteration
Inter-project feedback: no, only in terms of war-stories.

## Slide 75: Key Process Areas for Level 2 (Repeatable Process)
Requirements Management: Requirements are baselined in a project agreement and maintained during the project
Project Planning and Tracking: A software project management plan is established at the beginning of the project and is tracked during the project.
Subcontractor Management: The organization selects and effectively manages qualified software subcontractors.
Quality Assurance Management: All deliverables and process activities are reviewed and audited against standards and guidelines adopted by the organization.
Configuration Management: Controlled items are defined and maintained throughout the entire project.
Notes: Focus: Establish basic project management controls.
Requirements Management: Requirements are baselined in a project agreement and maintained during the project
Project Planning and Tracking: A software project management plan is established at the beginning of the project and is tracked during the project.
Subcontractor Management: The organization selects and effectively manages qualified software subcontractors.
Quality Assurance Management: All deliverables and process activities are reviewed and audited to verify that they comply with standards and guidelines adopted by the organization.
Configuration Management: A set of configuration management items is defined and maintained throughout the entire project.

## Slide 76: Key Process Areas for Level 3 (Defined Process)
Organization process:
  Permanent team maintains software life cycle.
  A standard software life cycle model is used for all projects.
Training program: The organization identifies training needs and develops training programs.
Integrated Software management: Each project can tailor their specific process from the standard process.
Software product engineering: Software is built according to the software life cycle, methods and tools.
Inter-group coordination: The project teams interact with other teams to address requirements and issues.
Peer reviews: Deliverables are reviewed on a peer level to identify defects and areas where changes are needed.
Notes: Focus: Establish an infrastructure that allows a single effective software life cycle model across all projects.
Organization process focus: The organization has a permanent team to constantly maintain and improve the software life cycle.
Organization process definition: A standard software life cycle model is used for all projects in the organization. A database is used for software life cycle-related information and documentation.
Training program: The organization identifies the needs for training for specific projects and develops training programs.
Integrated Software management: Each project has the possibility to tailor their specific process from the standard process.
Software product engineering: The software is built in accordance with the defined software life cycle, methods and tools.
Intergroup coordination: The project teams interact with other teams to address requirements and issues.
Peer reviews: Developer examine deliverables on a peer level to identify potential defects and areas where changes are needed.

## Slide 77: Key Process Areas for Level 4 (Managed Process)
Quantitative process management:
  Productivity and quality metrics are defined and constantly measured across the project.
  These data are not immediately used during the project, but are stored in a database to allow for comparison with other projects.
Quality management:
  The organization has defined a set of quality goals for software products. It monitors and adjusts the goals and products to deliver high-quality products to the user.
Notes: Focus: Quantitative understanding of the software life cycle process and deliverables.
Quantitative process management: Productivity and quality metrics are defined and constantly measured across the project.
It is critical that these data are not immediately used during the project, in particular to assess the performance of developers, but are stored in a database to allow for comparison with other projects.
Quality management: The organization has defined a set of quality goals for software products. It monitors and adjusts the goals and products to deliver high-quality products to the user.

## Slide 78: Key Process Areas for Level 5 (Optimized Process
Defect prevention: Failures in past projects are analyzed, using data from the metrics database.
Technology change management: Technology enablers and innovations are constantly investigated.
Process change management: The software process is constantly changed to deal with problems identified by the software process metrics.
Notes: Focus: Keep track of technology and process changes that may cause change in the system model or deliverables even during the duration of a project.
Defect prevention: Failures in past projects are analyzed, using data from the metrics database. If necessary, specific actions are taken to prevent those defects to occur again.
Technology change management: Technology enablers and innovations are constantly investigated and shared throughout the organization.
Process change management: The software process is constantly refined and changed to deal with inefficiencies identified by the software process metrics. Constant change is the norm, not the exception.

## Slide 79: Steps to Take in Using Metrics
Metrics are useful only when implemented in a careful sequence of process-related activities.
1. Assess your current process maturity level
2. Determine what metrics to collect
3. Recommend metrics, tools and techniques
  whenever possible implement automated support for metrics collection
4. Estimate project cost and schedule and monitor actual cost and schedule during development
5. Construct a project data base:
  Design, develop and populate a project data base of metrics data.
  Use this database for the analysis of past projects and for prediction of future projects.
6. Evaluate cost and schedule for accuracy after the project is complete.
7. Evaluate productivity and quality
  Make an overall assessment of project productivity and product quality based on the metrics available.