## Slide 1: Project Organization

## Slide 2: Where are we?
Software Process
  Build and Release Management
  System Testing
  Software Lifecycle Modeling
  Rationale Management
  Methodologies
Software Project Management
  Work Breakdown Strategies
  Estimation
  Scheduling
  Organization
  Planning and Controlling

## Slide 3: The End of the Tunnel
Software Process
  Build and ReleaseManagement
  System Testing
  Software Lifecycle Modeling (Next week)
  Rationale Management
  Methodologies (Last Lecture)
Software Project Management
  Work Breakdown Strategies
  Estimation
  Scheduling
  Organization (Today)
  Planning and Controlling (In 2 weeks, Agile Project Management)
Notes: Let’s start with an example

## Slide 4: Organizational Issues when define a Project
Every time, you set up a project, the same set of organizational issues appear
  What are the cost/benefits (“pros and cons”)?
  How should the teams be organized?
  Who are the key players?
    What roles and responsibilities do they assume?
    Who is in charge?
    What is the information flow between roles?
  What are the risks?
Architecture-centric project management
  Formulate software architecture (documented in the system design document) simultaneously with project organization (documented in the SPMP)
  Good Book: Paulish 2001 (see additional readings).

## Slide 5: Architecture-centric Project Management: 3 Steps
Define the subsystem decomposition
  Heuristics:
    Each service is realized by one subsystem
    Additional subsystems are determined by the software architectural style
  The initial version is often called the top-level design
Determine the work breakdown structure
  Heuristics:
    Tasks are based on the subsystem decomposition
    Also: Architectural & Project Management tasks
Set up the teams
  Heuristics:
    Each subsystem is assigned to one team
    Architectural and Project Management teams

## Slide 6: Setting up a Project: Example
1. Define Subsystem decomposition (“Top-Level Design”)
UserInterface
Control
Database
2. Determine the Work Breakdown Structure
Develop
Develop Database
Subsystem
Develop Control
UserInterface
Subsystem
Develop
System
Notes: Here we have a system that has been decomposed into 3 subsystems. To develop the system in a project, we broke the problem down into work to be performed. So first, we developed the work breakdown structure.
The next task is now to identify the resources, that can perform the identified work. This is the task of the project organization

## Slide 7: Setting up a Project: Example
2. Determine the Work Breakdown Structure
Develop
Develop Database
Subsystem
Develop Control
UserInterface
Subsystem
Develop
System
3. Set up the Teams
UserInterface
:Team
Control
:Team
Database
:Team
Notes: To develop the system in a project, we can assign a team to each of the subsystems.
In this example, we have the work assigned to 3 teams.
Every time, you do a project organization, the same set of issues appear:
  How are the teams organized?
  Who are the Key players?
  What Roles and Responsibilities do they assume?
  Structure: What is the information flow between roles
  Benefits and Challenges (“pros and cons”)
Paulish‘s book on architecture-centric project management contains a detailed description of the
the opportunities when the software architecture is formulated simultaeneously with the SPMP

## Slide 8: Group vs. Team
Group
  A set of people who are assigned to a common task and who work individually to accomplish their assignment
Team
  A small group of people working on the same problem or sub-problem in a project. The team members - also called participants - depend on one another to do their tasks.
Notes: Committee: Comprised of people who come together to review and critique issues
and propose recommendations for action.
Project Team
  Based on the premise that every participant must make a valuable contribution to the project.

## Slide 9: Organization
Organization
  A set of organizational units and their different relationships with each other
Organizational units can be organized according to many different categories
  by function, by project type, …
Typical examples of organizational units:
  Functional organization
    Research, Development, Marketing, Sales
  Project-based organization
    Project 1, Project 2, Project 3.

## Slide 10: Structures in Organizations
An organization usually has 3 different types of associations between organizational units
  Reporting structure
    Shows how status information is reported
  Decision structure
    Shows how decisions are propagated
  Communication structure
    Shows how information is exchanged.

## Slide 11: Roadmap for the Lecture
Discussion of different organization forms
  Functional organization
  Project-based organization
  Matrix organization
Binding roles to people in organizations
  Project manager, team member, developer, analyst, …
  Responsibility, Authority, Accountability and Delegation
Relationships between roles
  Hierarchical and Nonhierarchical organizations
Identifying people
  Audience list, drivers, supporters, observers
  Involvement of audience list members during the lifetime of a project.
Notes: We will first discuss different organization forms
Then we talk about the different roles played by people in these organizations
Then we discuss relationships between the roles

## Slide 12: Functional Organization
In a functional organization people are grouped into departments, each of which addresses an activity (“function”)
Examples of departments
  Traditional companies: Finance,production,sales,marketing
  Software companies: Analysis,design,integration,testing
Properties of functional organizations
  Projects are pipelined through the departments.
    Example: The project starts in research, moves to development, then moves to production
  Different departments often address identical needs
    Example: Configuration management, IT infrastructure
  Only few participants are involved in the complete project.
Notes: In software companies the departments correspond to the activities in the software process: Analysis, design, integration, testing departments.

## Slide 13: Example of a Functional Organization
Executive Office
Finance
Production
Sales
Marketing
Region1
Region2
IT
Region1
Region2
IT
Region1
Region2
IT
Region1
Region2
IT
Line organization of a „traditional business“
Notes: Finance, Production, Sales and Marketing are called departments

## Slide 14: Properties of Functional Organizations
Advantages:
  Members of a department have a good understanding of the functional area they support
Disadvantages:
  It is difficult to make major investments in equipment and facilities
  High chance for overlap or duplication of work among departments.
Notes:     It is difficult to make major investments in equipment and facilities
    Example: Two departments with a budget of 50,000 Euro each need a printer that costs 100,000 Euro.
    Both need only 50% of the maximum capacity.
    Neither department can buy it, because they don‘t have sufficient funds.

## Slide 15: Project-based Organization
In a project-based organization people are assigned to projects, each of which has a problem to be solved within time and budget
Key properties of project-based organizations
  Teams are assembled for a project as it is created
  Each project has a project leader
  All participants are involved in the complete project
  Teams are disassembled when the project terminates.

## Slide 16: Properties of Project-based Organizations
Advantages
  Very responsive to new requirements (because the project is newly established and can be tailored around the problem)
  New people can be hired who are familiar with the problem or who have special capabilities
  There is no waste of staff workload
Disadvantages
  Teams cannot be assembled rapidly. Often it is difficult to manage the staffing/hiring process
  Because there are „no predefined lines“, roles and responsibilities need to be defined at the beginning of the project.

## Slide 17: Matrix Organization
In a matrix organization, people from different departments of a functional organization are assigned to work on one or more projects
Project manager and participants are usually assigned to a project < 100 % of their time.
Executive Office
Finance
Production
Sales
Marketing
Project A
Project B
Participants of Project A
Participants of Project B

## Slide 18: Properties of Matrix Organizations
Advantages
  Teams for projects can be assembled rapidly
  Rare expertise can be applied to different projects as needed
  Consistent reporting and decision procedures can be used for projects of the same type
Disadvantages
  Team members usually are not familiar with each other
  Team member have different working styles
  Team members must get used to each other.

## Slide 19: Challenges in Matrix Organizations
Team members working on multiple projects have competing demands for their time
Team members must respond to two different bosses with different focus:
  Focus of the functional manager:
    Assignments to different projects, performance appraisal
  Focus of the project manager:
    Work assignments to project members, support of the project team
Multiple work procedures and reporting systems are used by different team members.
Notes: Team members working on multiple projects have competing demands for their time
  - Team members working on more than one project have even more project members to report to
  - Some people who have claim on the team member‘s time may be at similar levels in the organization‘s hierarchy
Multiple work procedures and reporting systems are used by different team members
  - Development of common procedures needs to be addressed at project kickoff time

## Slide 20: When to use a Functional Organization
Projects with high degree of certainty, stability, uniformity and repetition
  Requires little communication
  Role definitions are clear
The more people on a project, the more the need for a formal structure.
Notes: The more people on the project, the more need for a formal structure
  Examples:
    Customer might insist that the test team be independent from the design team
    Project manager insists on a previously successful structure
    These heuristics have worked well in previous project courses.
    It does not necessarily mean that they are successful in the current project.

## Slide 21: When to use a Project-based Organization
Project has high degree of uncertainty
  Open communication needed among members
  Roles are defined on project basis
When?
  Requirements change during development
  New technology appears during project.

## Slide 22: Meta-Model for Organizations
Functional
Organization
Project-based
Organization
Matrix
Organization

## Slide 23: Roadmap for the Lecture
We discussed different organization forms
  Functional organization
  Project-based organization
  Matrix organization
Now we will talk about the different roles played by people in these organizations
  Project manager, team member, developer, analyst, ….
  Responsibility, Authority, Accountability and Delegation.

## Slide 24: Definition Role
A role is a set of commitments to achieve specific results
A role is instantiated during a project and assigned to one or more participants
Instances of roles are often also called players („who are the key players?“) or stakeholders.

## Slide 25: Binding Roles To People
Project To-Do List
(from your WBS)
• Item 1
• Item 2
• Item 3
• Item 4
• Item 5
• Item 6
• Item 7
• Item 8
• Item 9
Item 1
Item 2
Item 9
Role 1
Item 4
Item 5
Item 7
Role 2
Item 3
Item 6
Item 8
Role 3
Person A
Person B
Role 1
Role 2
Role 3
To-Do Role Bindings are made during Project-Initiation Phase
Roles-Person Bindings are
made during Initial Planning phase
(First team meeting, etc …)

## Slide 26: Flexibility of Organizations
An organization is flexible, if it allows “late” or even “dynamic” bindings of roles to people and the information flow between roles
Late binding
  Organizational units and information flows are established just in time for the project
  Cannot be changed after project kickoff
Dynamic binding
  The organizational relationship changes over time
  Can be changed anytime.
Notes:   We recognize the fact that organizational units change over time
    New teams can be formed, Existing teams can be merged, An existing team can be removed
    from the organization
This means the organization must be flexible. We can achieve this by allowing flexible bindings between roles
and people.
Late binding
  Example: The top level design influences the team structure: At kickoff each subsystem is assigned to a team
Dynamic binding
  Example: We start with a hierarchical organization at project kickoff and end with a nonhierarchical organization at project finish time.

## Slide 27: Different Types of Binding Roles to People
One-to-One
  Ideal but often not worth to be called a project
Many-to-Few
  Each project member assumes several roles ("hats")
  Danger of over-commitment
  Need for load balancing
Many-to-"Too-Many"
  Some people don't have significant roles
  Bystanders
  People loose the touch with project.

## Slide 28: Key Concepts for Binding Roles to People
Responsibility
  The commitment to achieve specific results
  Redefinition of role: A role is a set responsibilities
Delegation
  Rebinding a responsibility assigned to one person (including yourself) to another person.
Authority
  The ability to make the binding decisions between roles and people
Accountability
  Tracking a task performance to a person

## Slide 29: Three Reasons for Delegation
Time Management: Free yourself up to do other tasks
Expertise: Select a better qualified person to make the decision
Training: To develop another person’s ability to handle additional assignments.
One can delegate authority, but not responsibility
One can share responsibility
  Delegation and sharing relationships between activities and roles are always associated with risks
Notes: Once more: Delegation is the binding of a responsibility assigned to one person (including yourself) to another person

## Slide 30: Identification of Responsibility Risks
Risk: Somebody is heavily committed.
  Possible Project Management Issues:
    Person does not have time to handle all tasks
    Person is making too many key decisions
    What if this person leaves during the project?
Risk: Project manager has no direct responsibilities
  Will the project manager understand status reports?
Risk: An activity requires many approvals
  Does anyone else have to approve the activity?
  Are there too many people involved in the approvals?
  Is the estimated duration of the activity too optimistic, because the approval is out of your hands?
Notes: Analysing Responsibility Charts identifies Risks
After identify an issue, you should address it in in the software project management plan.
Examples of risks:
Risk: Somebody is heavily committed.
  Possible Project Management Issues:
    Person does not have enough time to handle all tasks
    Person is making too many key decisions
    What if this person leaves during the project?
Risk: The project manager has no direct responsibilities
  Will the project manager fully understand status reports?
Risk: An activity requires many approvals
  Does anyone else have to approve the activity?
  Are there too many people involved in the approvals?
  Is the estimated duration of the activity too optimistic, because the approval is out of your hands?

## Slide 31: Authority vs. Responsibility
Both are upfront agreements
    Before you start a project, you agree on who can make decisions and who will ensure that particular results are achieved
Difference:
  Authority is activity-oriented: It focuses on process such as activities and tasks
  Responsibility is entity-oriented: It focuses on outcome such as work products and deliverables.
Notes: Authority: The ability to make the binding decisions between roles and people
Responsibility: The commitment to achieve specific results

## Slide 32: Authority vs. Responsibility vs. Accountability
Authority vs. Responsibility
  Similarity: Before you start a project, you agree on who can make decisions and who will ensure that particular results are achieved.
  Difference: Authority focuses on process, responsibility focuses on outcome
Responsibility vs. Accountability
  Similarity: Both focus on results
  Difference: Responsibility is a before-the-fact agreement, accountability is an after-the-fact process
Notes: Authority vs Responsibility
  They are similar: Both are upfront agreements. Before you start a project, you agree on who can make decisions and who will ensure that particular results are achieved.
  They are different: Authority focuses on process such as activities and tasks, responsibility focuses on outcome such as work products and deliverables
Responsibility vs Accountability
  Similarity: Both focus on results
  Difference: Responsibility is a before-the-fact agreement, accountability is an after-the-fact process.
  If you are responsible you should be held accountable.
  If you are not responsible you should not be held accountable.
  Scapegoating: Making somebody accountable who was not responsible

## Slide 33: Responsibility vs. Accountability
Both are entity-oriented (focus on the result!):
Difference:
  Responsibility is an agreement done before a task started
  Accountability is investigated after a task is performed
A person who is responsible is also accountable
A person who is not responsible is not accountable
  Scapegoating: Making somebody accountable who was not responsible
Delegation of responsibility is associated with risks.
Notes: Responsibility: The commitment to achieve specific results
Accountability: Tracking a task performance to a person

## Slide 34: Risks when Delegating Responsibility
Risk: Responsible person is over-committed
  Project Management Issues:
    Person does not have enough time to handle all roles
    Person is making too many key decisions
    What if this person leaves during the project?
Risk: The project manager has no longer any responsibilities (“everything was delegated”)
  Will the project manager understand the status reports?
Risk: The outcome requires additional approvals
  Does anyone else have to approve the outcome?
  Are there too many people involved in the approvals?
  The estimated duration of the activity may be too optimistic, because it is overlooked, that the approval involves many people.
Notes: Analysing Responsibility Charts identifies Risks
After identify an issue, you should address it in in the software project management plan.

## Slide 35: Key Roles in Projects
Project Manager: The person responsible for the successful completion of the project
Team Member: Participants responsible for performing activities and tasks (in a project or matrix organization)
Functional Manager: The team member‘s supervisor in the department (in a functional organization)
Upper management: People in charge of the departments or projects (“program manager”)
In the following we focus only on roles in project-based organizations.

## Slide 36: Responsibilities of the Project Manager (1)
Determine objectives, schedule and resources
Design a software project management plan
Create and sustain focused and motivated teams
Determine the team‘s work procedures, reporting systems and communication infrastructure

## Slide 37: Responsibilities of the Project Manager (2)
Accomplish project objective within time & budget
Monitor performance against the plan
Resolve technical and interpersonal conflicts
Control changes in the project
Report on project activities to upper management
Keep the client informed and committed
Contribute to the team members performance approval

## Slide 38: General Responsibilities of Team Members
Technical responsibilities:
  Perform assigned tasks within time
  Acquire technical skills and knowledge needed to perform the work
Managerial responsibilities
  Identify situations and problems that might affect the tasks
  Keep others informed about your progress and problems you encounter.

## Slide 39: Typical Project Roles
Project Management
  Coach
  Team leader
  API Liaison
  Planner
Meeting Management
  Minute Taker
  Scribe
  Primary facilitator
Development
  Analyst
  Designer (Software Architect)
  Programmer
  Tester
  Maintainer
  Trainer
  Document Editor
  Web Master
  Configuration Manager

## Slide 40: A Taxonomy for Project Roles
Management role
  Organization and execution of the project within constraints. Examples: project manager, team leader
Development role
  Specification, design and construction of subsystems. Examples: Analyst, software architect, programmer
Cross functional role
  Execute project functions. Examples: API Liaison, configuration manager
Consultant role
  Supports in areas where project participants lack expertise. Examples: End user, client, application domain specialist (problem domain), technical consultant (solution domain)
Promoter role
  Deals with change in organization, application/solution domain, software process.

## Slide 41: Promoter
Promoters are self appointed individuals who identify themselves with the outcome of the project
  They are member of the corporate organization and may not necessarily be directly involved with the project
  Instead, they are the interface to the rest of the corporate organization
Able to push specific changes through the existing organization which are needed to make the project a success
Power promoter, knowledge promoter, process promoter.
Notes: Because of their power, knowledge of technology, or familiarity with the project’s processes, they are able to promote and push specific changes through an existing organization which are needed to make the project a success.

## Slide 42: Power Promoter
Also called project champion
Pushes the change through the existing organizational hierarchy
  not necessarily at the top of the organization, but must have protection from top level management, otherwise project opponents might be able to prevent the success of the project
Tasks:
  Constantly identify difficulties, resolve issues, and communicate with the project members, especially with the developers
Example at project level: Project Leader
Example at corporate level: Chief Executive Officer (CEO)

## Slide 43: Knowledge Promoter
Also called the technologist
Promotes change arising in the application domain or the solution domain. Usually closely associated with the power promoter
Tasks: Acquire information iteratively, understand the benefits and limitations of new technologies, and argue its adoption with the other developers
Example at project level: System architect
Example at corporate level: Chief Technical Officer (CTO).
Notes: Example at project level: System architect.
  Reports to project manager
  Does not have any direct subordinate in the reporting hierarchy
  Has final say over all technical decisions in the system

## Slide 44: Process Promoter
The process promoter has intimate knowledge of the projects processes and procedures
The process promoter is in constant interaction with the power promoter to get consensus on the overall goals
Tasks: Bridge between the power and knowledge promoters, who often do not speak or understand the same language
Example at project level: Development lead
Example at corporate level: Chief Information Officer (CIO).
Notes: Example at project level: Development lead.
Responsible for the administrative aspects of a project, including planning, milestones definition, budgeting and communication infrastructure.

## Slide 45: Roadmap for the Lecture
We first discussed different organization forms
  Functional Organization
  Project Organization
  Matrix Organization
Then we talked about the different roles played by people in these organizations
  Taxonomy of roles: Project Manager, Team Member, Upper Management,….,Promoters
  “Dynamic model” of roles: Responsibility, Authority, Accountability and Delegation
Now we discuss different types of relationships between the roles
  Hierarchical Organizations
  Nonhierarchical Organizations.

## Slide 46: Relationships between Roles
Organizations can have many different types of associations between roles
The three most important associations for project organizations are: Reporting, decision making and communicating
Reporting association
  Used for reporting status information
Decision association
  Used for propagating decisions
Communication association
  Used for exchanging information needed for decisions (e.g., requirements, design models, issues).

## Slide 47: An Organization with Reporting and Decision Structure
UserInterface
:SubsystemTeam
Database
:SubsystemTeam
Control
:SubsystemTeam
decision
status
decision
status
Management
:Team
Notes: The developers make local decisions and report them via a status report to the leader (this can be either the team leader or the project manager)
The team leader, who has an overview of the subsystem, can override these decisions. Provides status to the project manager.
The project manager, who has a global view of the project, can virtually override any decision.

## Slide 48: An Organization with Distinct Reporting, Decision and Communication Structures
Notes: Developers communicate with each other without having to communicate with the team leader or project leader.
Developers make local decisions and report them to the leader
  The team leader, who has a local overview of the subsystem, can override these decisions. She reports them to the project manager.
  The project manager, who has a global view of the project, can virtually override any decision.

## Slide 49: Hierarchical Organization
Often also called centralized organization. Examples: Military, church, traditional businesses
Key properties
  The organization has a tree structure
  Decisions are made at the root and communicated to the leaf nodes
  The decision association is also used for reporting and communication.

## Slide 50: Hierarchical Project Organization
Chief Executive
First Level Manager
(“Front-Line Manager”)
Project Members
Basis of organization:
Complicated information and control flow
across hierarchical boundaries
A
B
A wants to talk to B: Complicated Information Flow
Control Flow
Information Flow
B wants to make sure A does a certain change: Complicated Controlflow

## Slide 51: Advantages of Hierarchical Organizations
Centralized control over project selection
One set of management and reporting procedures for all project participants across all projects
Established working relationships among people
Clearly established lines of authority to set priorities and resolved conflicts
Authority to pressure people to honor their action items
Clearly defined career path.

## Slide 52: Example of a Hierarchical Organization from the early IT Days : Chief Programmer Team [Brooks 1995]
Chief Programmer
Librarian
Administration
Tester
Junior Programmer
Assistant
Chief Programmer
Senior Programmer
Notes: Totally hierarchical
Talk about the roles: Chief the main dictator, assistant joined the company 2 years ago...
Batch oriented
When talking abou the libriarian, play somebody who is pushing a shopping cart at the Giant Eagle: Dispatching the lineprinter printouts to the various offices!!

## Slide 53: Disadvantages of Hierarchical Organizations
Slow response time
  Evaluating and approving change requests takes too long because of long reporting/decision lines
Difficult to manage the workload of the people
  People are fulltime members of the organization, but projects don’t come in a steady stream
  Project might not require the available people
Problems with application or solution domain
  People are hired for their technical proficiency in a specialty that the organization normally performs.
  Often they have only limited experience, if the problem to be solved is outside their field of expertise.

## Slide 54: Nonhierarchical Organizations
An organization that can be described with a general graph structure
  different edges for the decision, reporting and communication flows
  Decisions can be made at various nodes in the graph.

## Slide 55: Nonhierarchical Project Organization
Project
Leader
Coaches
Team
Members
Basis of organization:
Nonlinear information flow across dynamically formed units
Subsystem Team
Subsystem Team
Subsystem Team
A
B
B wants to make sure A does a certain change: Decision Flow
A wants to talk to B: Communication Flow
Notes: Project-based organizations create bridges within organizations and bridge boundaries outside with customers, suppliers, and competitors. Teams are the foundation unit of these new patterns of interconnection and interdependence. Telecommunications technology is the nervous system that holds these networks together. Groupware is the collaboration support technology that shapes and holds the activity of teams within those networks."
Project-based organizations are based on the fct that ever-shifting networks of teams that cross traditional, formerly forbidden boundaries, linking once-competing organizations into ecosystems of cooperation

## Slide 56: A Nonhierarchical Organization: Egoless Programming [Weinberg 1971]
Analyst
Designer
Librarian
Tester
Programmer

## Slide 57: Observations on Organizational Structures
Hierarchical structure
  “Reports”, “Decides” and “Communicates-With” are all mapped onto the same association
  Does not work well with iterative and incremental software development processes
  Manager is not necessarily always right
Nonhierarchical structure
  “Reports”, “Decides” and “Communicates-With” are modeled as different associations
  Cuts down on bureaucracy
  Reduces development time
  Decisions are expected to be made at each level
  Hard to manage.

## Slide 58: Final Topic for Today: Identifying People
Organizational Structures
  Functional, Project and Matrix Organizations
Taxonomy for roles (Object model)
  Project Manager, Team members, upper management, ...
States of a role (Dynamic model)
  Responsibility, Authority. Accountability and Delegation
Project functions involving roles (Functional model)
  Decision making, status reporting, communication
Another taxonomy of people
  Audience List, Drivers, Supporters, Observers
  Involvement of audience members during the lifetime of a project.

## Slide 59: Identifying People
Audience List: A list of people or groups of people that support the project or are simply interested in it
As soon as you start thinking about a project, you should start the audience list
It is a good idea to start with a template
  Audience List Template.
Notes: The template can be from previous projects. Ask for other project managers for it. For sure they have one!

## Slide 60: Categories for an Audience List Template
Internal
  Project manager
  Upper management
  Requester
  Team members
  People with special knowledge
External
  Clients or customers
  Collaborators
  Vendors, suppliers and contractors
  Regulators
  The general public
Support Groups
  Human Resources
  Legal services
  Contracting
  Finances
  Security
  Computing Facilities
End users of the project‘s deliverables
People who will maintain or support the deliverables.

## Slide 61: Guidelines for the Audience List
Use a template that worked well in a previous project
Speak with a wide range of people
Encourage project participants to identify additional candidates
Instantiate instances from each category with position and name
Separately include a person‘s name for every different role played by him or her
Allow sufficient time to developing the audience list (mainly during project initiation time).
Notes: Continue to maintain the audience list during the project (remove names, add names)

## Slide 62: Other Categories for the Audience List
Drivers
  People who have some say in defining the results of the project
Supporters
  People who help to perform the activities and tasks of the project
Observers
  People who are interested in the activities and results of the project
Project Champion
  A person who strongly supports the project, even advocates it in disputes
  Takes whatever is necessary to help ensure the successful completion of the project.
Notes: Supporters include those who authorize resources for the project as well as those who work on it.
Beware of supporters who act like drivers!
Observers have no say in the project and they are not actively involved. However, the project may affect them at some point in the future.
The project champion is a Power Promoter.

## Slide 63: Methods to keep the Audience involved
One-on-one meetings
  Formal and informal meetings with one or two other participants about project issues
Group meetings
  Planned session for some or all project team members (weekly meeting), the client (reviews) or other members of the audience list
Informal written correspondence
  Notes, memos, letters and e-mail to document informal discussions and to share important project information
Written approvals
  Formal written agreements about a work product, schedule, resource commitment or a technical approach.

## Slide 64: Other Project Lists
Stakeholder list
  Identifies people and groups who support or are affected by your project
  This list does not include people outside of the organization or those who are merely interested in the project
Distribution Lists
  Identifies people who receive copies of written project communication.
  The presence of people on distribution lists does not ensure that they actually support the project (Often out of date)
Team member lists
  People whose work is directed by the project manager.

## Slide 65: Heuristics for a Successful Project Manager
1. Create a team identity
  Clarify team vision and working relationships among participants
  Define team procedures (meeting management, configuration management and system integration strategy)
  Clarify each participant‘s role
2. Create team member buy-in
  Get commitment to project goals (difficult in matrix organizations)
  Get to know other people‘s style
3. Get support from the environment
  Get a project champion (for example a power promoter)
4. Develop general procedures
  Procedure for conflict resolution
  Procedures for communication between teams and project manager, with upper management and with the client
5. Avoid Micro Management.

## Slide 66: Micromanagement
Micromanagement is the excessive involvement of a person in the details of a task assigned to another person
Micromanagement is inefficient use of the time and energy of all project participants
It leads to tension and low morale among all project members
Why do people micro-manage?

## Slide 67: Reasons for Micromanagement
The manager is interested the work and enjoys it
The manager is a technical expert who feels best fitted for the job
The manager feels the assignment was not explained clearly
The manager is looking for a way to stay involved with the person or the team
The manager feels threatened because the managed person has more technical knowledge
The manager does not have a clear understanding on how to spend project time
The manager wants to stay up-to-date in case somebody else asks about the work.

## Slide 68: Overcoming Micro Management
Don‘t be defensive when the manager asks questions
  Otherwise it looks as if you are hiding something and the manager will worry even more
Thank the micromanager for the interest and time
  Complaining about micromanagement will cause the micromanager to do it even more
Offer to explain to the micromanager how you will approach your tasks
Work out at scheme for sharing progress and accomplishments.

## Slide 69: Summary
Organization: A graph with nodes (organizational units) and different type edges (information structures
  Functional, project-based and matrix organization
Teams are the key to project-based organizations
Flexibility of organizations
  Dynamic binding of responsibilities to people
Project roles in project organizations
Authority, Responsibility, Accountability, Delegation („dynamic model of the organization“)
  Delegation involves risks.
Notes:   Functional Organization: Organizational units are business functions or software process activities („functional model of the organization“)
  Project Organization: Organizational units are teams. („object model of the organization“)
  Matrix Organization: Organization that inherits the properties of both, functional and project organizations.
  Hierarchical organization: Tree with only one type of information structure used for everything (decisions, status, communication).
  A Responsibility Chart: Shows team roles and responsibilities. Can help to identify and avoid potential difficulties during a project

## Slide 70: Additional References
D. J. Paulish, Architecture-centric Software Project Management , SEI Series in Software Engineering, Addison-Wesley, 2001
E. Raymond, The cathedral and the bazaar,http://www.tuxedo.org/~esr/writings/cathedral-bazaar/cathedral-bazaar.html, 1998
F. P. Brooks, The Mythical Man Month: Essays on Software Engineering. Addison-Wesley, Reading, MA, 1995
G. M. Weinberg, The Psychology of Computer Programming, Van Nostrand, New York, 1971.
J. Hauschildt, H. G. Gemünden (Hrsg.): Promotoren. Champions der Innovation, 2nd edition, in German, 1999.
Notes: Paulish‘s book on architecture-centric project management contains a detailed description of the
the opportunities when the software architecture is formulated simultaeneously with the SPMP
Raymonds article describes the positive impact of nonhierarchical organizations in the software projects.
  See also Hauschild about Innovation Management. J. Hauschildt, S.Salomo: Innovationsmanagement, 4th edition, in German, 2007
Innovation vs Invention (in German)
Nach Joseph Schumpeter (Theorie der wirtschaftlichen Entwicklung, 1911) ist Innovation die Durchsetzung einer technischen oder organisatorischen Neuerung im Produktionsprozess, nicht schon die entsprechende Erfindung.
Innovator ist für Schumpeter der schöpferische Unternehmer (im Gegensatz zum Arbitrageunternehmer, der lediglich vorhandene Preisunterschiede zur Gewinnerzielung ausnutzt), der auf der Suche nach neuen Aktionsfeldern den Prozess der schöpferischen Zerstörung antreibt. Seine Triebfeder sind auf der Innovation basierende kurzfristige Monopolstellungen, die dem innovativen Unternehmer Pionierrenten verschaffen. Das sind geldwerte Vorteile (auch Innovationspreise), die durch die innovativen Verbesserungen entstehen, zum Beispiel durch die höhere Produktivität einer Prozessinnovation oder durch höhere Monopolpreise einer Produktinnovation.
Laut Jürgen Hauschildt geht es bei einer Innovation grundsätzlich um etwas "Neues": Neue Produkte, neue Märkte, neue Verfahren, neue Vorgehensweisen, neue Prozesse, neue Vertriebswege, neue Werbeaussagen und vieles mehr. Innovationen sind in Ihrem Ergebnis etwas "neuartiges", die sich gegenüber dem vorangegangenen Zustand merklich unterscheiden. Diese Neuartigkeit muss wahrgenommen, muss bewusst werden. Die Neuartigkeit besteht darin, dass Zwecke und Mittel in einer bisher nicht bekannten Form miteinander verknüpft werden. Diese Verknüpfung muss sich auf dem Markt oder innerbetrieblich (wirtschaftlich) bewähren. So kann ein gegebener Zweck (zum Beispiel Antrieb eines PKW) mit neuen Mitteln (Wasserstoff, Autogas, Erdgas etc.) erreicht werden oder mit gegebenen Mitteln (beispielsweise bestehender Telefonleitung) ein neuer Zweck geschaffen werden (Nutzung auch zur Datenübertragung für das Internet). Die reine Hervorbringung einer Idee genügt allerdings nicht – erst Verkauf oder Nutzung unterscheidet eine Innovation von der Invention.

## Slide 71: Backup slides

## Slide 72: Linear Responsibility Chart
A linear responsibility chart is a matrix that depicts the role that each project participant will play in different activities identified in the work breakdown structure.
Rows: Project activities
Columns: Roles/Project participants
Entries: Type of responsibility
  P (Primary responsibility): You have committed to ensure that the desired result is achieved
  S (Secondary responsibility): You have committed to some portion of the result
  A (Approval): You are not doing the work, but you will approve what has been done
  R (Review): You will review and comment on the work product of an activity
  O (Output): You will receive the work product of an activity
  I (Input): You will provide input for a task or activity

## Slide 73: Example of a Responsibility Chart
Project Team Team Team
Manager Leader Member A Member B
Develop SPMP
P
Run weekly
meeting
A
S
P
Write SDD
P
S
S
S
  Legend:
  P = Primary responsibility
  S = Secondary responsibility)
  A = Approval

## Slide 74: Another Example of a Responsibility Chart
Project Team Team Team
Manager Leader Member A Member B
Develop SPMP
A
P
• The Project Manager has delegated the
SPMP to Team Member A
• The delegation bypasses the team leader
Is that a problem?
• Team Member B helps by writing a
section.
S

## Slide 75: Responsibilities of the Project Manager
Determine objectives, schedule and budgets
Design software project management plan (SPMP)
Establish focused and motivated teams
Determine work procedures, reporting systems and communication infrastructure
Accomplish project objective within time & budget
Monitor performance against the plan
Resolve technical and interpersonal conflicts
Report project activities to upper management
Keep the client informed and committed
Contribute to or describe the team members performance approval.

## Slide 76: Responsibilities of the Coach
Listen to gripes from individual team members
Attend weekly project meetings
Review weekly team status reports
Schedule and prepare meetings with project manager
Insist that project guidelines are followed
Assign presentations to team members (in-class project meetings, client review, client acceptance test)
Resolve team member conflicts if they cannot be resolved otherwise

## Slide 77: Responsibilities of the Team Leader
Responsible for intra-team communication (Meeting Management: Primary Facilitator)
  Run the weekly project meeting
  Post the agenda before the meeting
  Define and keep track of action items assigned to team members (who, what, when)
  Measure progress (Enforce milestones)
  Deliver work packages for the tasks to the project manager
  Present team status to project manager
Important heuristics: The team leader should be rotated among members of the team.
Notes: Role switching: Used to work well for smaller groups. We still encourage switching of group leaders, but now for smaller times

## Slide 78: Team Leader: Create an Agenda
Purpose of Meeting
Desired Outcome
Information Sharing
Information Processing
Meeting Critique
Action Items
(Check Previous
Meeting)
Issues
(Check Previous
Meeting & BBoards)

## Slide 79: Responsibilities of the API Liaison
Liaison: Single point of contact
In a project the team liaison is responsible for inter-team communication
  Coordinate tasks spanning more than one team with other teams
Responsibilities of the API Liaison:
  Make available public definitions of the subsystems developed by the team to the architecture team (ensure consistency, etc)
  Communicate the service specifications developed by the architecture team back to the development team.
Notes: Main Entry:li·ai·son Pronunciation:\ˈlē-ə-ˌzän, lē-ˈā-, ÷ˈlā-ə-\Function:nounEtymology:French, from Middle French, from lier, from Old FrenchDate:circa 1648
1: a binding or thickening agent used in cooking
2 a: a close bond or connection : interrelationship b: an illicit sexual relationship : affair 3a
3 a: communication for establishing and maintaining mutual understanding and cooperation (as between parts of an armed force) b: one that establishes and maintains liaison
4: the pronunciation of an otherwise absent consonant sound at the end of the first of two consecutive words the second of which begins with a vowel sound and follows without pause

## Slide 80: Responsibilities of the Planner
Plans the activities of an individual team
Define project plan for team:
  Work Breakdown Structure
  Dependency graph and schedule showing work packages
Make project plan available to management
Report team project status to team leader No explicit planner in many teams Responsibility usually assumed by team leaders or project manager.

## Slide 81: Responsibilities of the Document Editor
Collect, proofread and distribute team documentation
Submit team documentation to documentation team
Collect agendas
Take minutes at meetings.

## Slide 82: Responsibilities of the Web Master
Maintain team home page
Keep track of meeting history
Keep track of design rationale.

## Slide 83: Web Master
Date
9/9/
Agenda
Minutes
Action Items
Issues
Agenda
Minutes
Action Items
Issues
9/16/
Agenda
Minutes
Action Items
Issues
Publish Meeting Information on Team Homepage
  Should contain agenda, minutes, action items and issues
  Possibilities:
    One HTML document per meeting, with anchors (maintained by one role)
    Separate HTML documents for Agenda, Minutes, etc (maintained by several roles)