## Slide 1
July 2
July 1
July 3
July 2
Using UML, Patterns, and Java
Object-Oriented Software Engineering
Estimation
West Rib 4 Days
Cassin Ridge 2 Days
July 4
July 1
Notes: If you want to climb McKinley, you have several alternatives:
West Rib: Takes 3 high Camps for normal climbers, 50-55 degrees at the crux
Second hardest route, but can be done by good climbers
Cassin: can be done with one Camp, hard climbing, the hardest route , only for very good climbers
The West Rib summit climb can be broken down into 4 tasks: Basecamp to Camp1, climb to Camp2, Climb to Camp 3, Climb to Summit.
Duration: 4 days to summit.
The summit via the Cassin ridge can be done in 2 days
2 days is shorter than 4 days. Which route should we do? Should you do the Cassin because it can be done in 2 days?
Not shown, but definitely a necessary task:-): Climb back to base camp, usually 1 day from summit back to base camp
Maybe neither the West Rib nor the Cassin ridge route, but the normal route, call the west buttress route? Technically easier, but still longer
BTW, the exceptional russian climber Anatoli Boukreev climbed the West Rib route solo in 10 hours!

## Slide 2: Revised Lecture Schedule
Apr 21: Introduction
Apr 28: Basic Concepts
May 5: Project Communication
May 13: Configuration Management
May 19: Build and Release Management
May 26: Estimation
June 02: No Lecture
June 09: Scheduling
June 16: Guest lecture
June 23: Project Organization
June 30: Lifecycle Modeling
July 7: Agile Project Management
July 14 : Guest Lecture
July 21: Lecture Review
July 30: Exam

## Slide 3: Revised Exercise Schedule
April 22: Icebreaker
April 29: Software Project Management Plan (Homework 1: Write an SPMP)
May 6: Project Agreement
May 13: Software Configuration Management Plan (Homework 2: Write an SCMP)
May 20: Continuous Integration (Hudson)
May 29: Work Breakdown structures
June 5: Estimation
June 10: Scheduling
June 24: Rationale Management
July 1: Student presentations of SPMP
July 8: Agile Project Management (Daily Scrum, Planning Poker)

## Slide 4: Objectives for Today
Build an understanding of…
Importance of estimations
Different estimation approaches (initial situation, expectations, top-down versus bottom-up…)
Advantages and disadvantages of different approaches
Common pitfalls

## Slide 5: Importance of Estimations
During the planning phase of a project, a first guess about cost and time is necessary
Estimations are often the basis for the decision to start a project
Estimations are the foundation for project planning and for further actions
   Estimating is one of the core tasks of project management, but still considered as black magic !
Notes: Estimations are part of the project business case
Estimations are the foundation for project planning (resources, staffing, project schedule) and for further actions (market entry, marketing, etc.)

## Slide 6: Challenges
Incomplete knowledge about:
  Project scope and changes
  Prospective resources and staffing
  Technical and organizational environment
  Infrastructure
  Feasibility of functional requirements
Comparability of projects in case of new or changing technologies, staff, methodologies
Learning curve problem
Different expectations towards project manager.
Notes: Different expectations towards project manager
buyer -> low estimation;
contractor -> at least “realistic” estimation…;
in general: “political” estimations; tendency to be optimistic
Learning curve problem: increasing productivity over time while staffing new personnel

## Slide 7: Problems with Estimations
Estimation results (effort and time) are almost always too high (for political / human reasons) and have to be adjusted in a structured and careful manner
Reviews by experts always necessary
New technologies can make new parameters necessary
Depending on the situation, multiple methods are to be used in combination.

## Slide 8: Guiding Principles
Documentation of assumptions about
  Estimation methodology
  Project scope, staffing, technology
Definition of estimation accuracy
Increasing accuracy with project phases
  Example: Better estimation for implementation phase after object design is finished
Reviews by experienced colleagues

## Slide 9: Components of an Estimation
Cost
  Personnel (in person days or valued in personnel cost)
    Person day: Effort of one person per working day
  Material (PCs, software, tools etc.)
  Extra costs (travel expenses etc.)
Development Time
  Project duration
  Dependencies
Infrastructure
  Rooms, technical infrastructure, especially in offshore scenarios
This lecture
Lecture on Scheduling.
Notes: person day = effort of one person per working day

## Slide 10: Estimating Development Time
Development time often estimated by formula
Duration = Effort / People
Problem with formula, because:
  A larger project team increases communication complexity which usually reduces productivity
Therefore it is not possible to reduce duration arbitrarily by adding more people to a project
In the lectures on organization and scheduling we take a more detailed look at this issue.
Notes: In general, Duration = Effort / People, but:
  A larger project team increases team communication complexity which usually reduces productivity
Therefore it is not possible to reduce duration arbitrarily by adding more people to a project
On the contrary, it can even take longer !
This leads us to the lecture on project organization and scheduling.

## Slide 11: Estimating Personnel Cost
Personnel type: Team leader, application domain expert, analyst, designer, programmer, tester…
Cost rate: Cost per person per day
2 alternatives for cost rate:
  Single cost rate for all types (no differentiation necessary)
  Assign different cost rates to different personnel types based onexperience, qualification and skills
Personnel cost: person days x cost rate.

## Slide 12: Estimating Effort
Most difficult part during project planning
  Many planning tasks (especially project schedule) depend on determination of effort
Basic principle:
  Select an estimation model (or build one first)
  Evaluate known information: size and project data, resources, software process, system components
  Feed this information as parametric input data into the model
  Model converts the input into estimates: effort, schedule, performance, cycle time.
Notes: Most important:
  • knowledge about project scope (what needs to be done)
  • reuse of software methodology (software lifecycle, work products, etc)
  • In general: lots of experience

## Slide 13: Basic Use of Estimation Models
Model
Parametric Data
Estimate
Examples:
Data Input Estimate
Size & Project Data Effort & Schedule
System Model Performance
Software Process Cycle Time

## Slide 14: How do you Build an Estimating Model?
Historical Data
Meta- Model of
Software Process
Estimating Model
Insight

## Slide 15: Calibrating an Estimation Model
Basic Estimation Model
Your Data
Your Experience
Calibrated Estimation Model
Your Insight

## Slide 16: Top-Down and Bottom-Up Estimation
Two common approaches for estimations
  Top-Down Approach
    Estimate effort for the whole project
    Breakdown to different project phases and work products
  Bottom-Up Approach
    Start with effort estimates for tasks on the lowest possible level
    Aggregate the estimates until top activities are reached.
Notes: Top down approach: Breakdown to different project phases and work products possibly by using percentages, for example: 10% for project management is a common number
Bottom-Up Approach: Estimation of work products on lowest possible level, then aggregation to top-level; possibly supplemented by some general percentages as in top down, for example: 10% for project management.

## Slide 17: Top-Down versus Bottom-Up (cont’d)
Top-Down Approach
  Normally used in the planning phase when little information is available how to solve the problem
  Based on experiences from similar projects
  Not appropriate for project controlling (too high-level)
  Risk add-ons usual
Bottom-Up Approach
  Normally used after activities are broken down the task level and estimates for the tasks are available
  Result can be used for project controlling (detailed level)
  Smaller risk add-ons
Often a mixed approach with recurring estimation cycles is used.

## Slide 18: Estimation Techniques
Expert estimates
Lines of code
Function point analysis
COCOMO I
COCOMO II

## Slide 19: Expert Estimates
= Guess from experienced people
No better than the participants
Suitable for atypical projects
Result justification difficult
Important when no detailed estimation can be done (due to lacking information about scope)

## Slide 20: Lines of Code
Traditional way for estimating application size
Advantage: Easy to do
Disadvantages:
  Focus on developer’s point of view
  No standard definition for “Line of Code”
  “You get what you measure”: If the number of lines of code is the primary measure of productivity, programmers ignore opportunities of reuse
  Multi-language environments: Hard to compare mixed language projects with single language projects
“The use of lines of code metrics for productivity should be regarded as professional malpractice” (Caspers Jones)
Notes: No standard definition for “Line of Code”: Do blank lines count? Do comments count? Do declarations count? What happens if a statement extends over several lines?

## Slide 21: Function Point Analysis
Developed by Allen Albrecht, IBM Research, 1979
Technique to determine size of software projects
  Size is measured from a functional point of view
  Estimates are based on functional requirements
Albrecht originally used the technique to predict effort
  Size is usually the primary driver of development effort
Independent of
  Implementation language and technology
  Development methodology
  Capability of the project team
A top-down approach based on function types
  Three steps: Plan the count, perform the count, estimate the effort.
Notes:   Size is measured from a functional point of view, not from a task view. In that sense function point analysis focuses more on the functional model (requirements analysis) than on the task model (project management). In other words, estimates are based on the users view of the functionality , not the developers view.
  However, the types of functions that Albrecht had in mind were transactions in a functionally decomposed system. Wether function points can be used to count use cases is an open question.
  Function points are not a perfect measure of effort to develop an application or of its business value, although the size in function points is typically an important factor in measuring each. This is often illustrated with an analogy to the building trades. A three thousand square foot house is usually less expensive to build one that is six thousand square feet. However, many attributes like marble bathrooms and tile floors might actually make the smaller house more expensive. Other factors, like location and number of bedrooms, might also make the smaller house more valuable as a residence.
  Historical note (From Ray Boehm: http://ourworld.compuserve.com/homepages/softcomp/fpfaq.htm)
  In the late seventies, IBM felt the need to develop a language independent approach to estimating software development effort. It tasked one of its employees, Allan Albrecht, with developing this approach. The result was the function point technique. In the early eighties, the function point technique was refined and a counting manual was produced by IBM's GUIDE organization. The International Function Point Users Group (IFPUG) was founded in the late eighties. This organization produced its own Counting Practices Manual. In 1994, IFPUG produced Release 4.0 of its Counting Practices Manual.

## Slide 22: Steps in Function Point Analysis
Plan the count
  Type of count: development, enhancement, application
  Identify the counting boundary
  Identify sources for counting information: software, documentation and/or expert
Perform the count
  Count data access functions
  Count transaction functions
Estimate the effort
  Compute the unadjusted function points (UFP)
  Compute the Value Added Factor (VAF)
  Compute the adjusted Function Points (FA)
  Compute the performance factor
  Calculate the effort in person days
Notes: Function Point Analysis is based on a functional decomposition of the system into input, transformation and output functions.
The Analysis consists of two steps: Planning the count, and performing the count.
A) Plan the Count. This step includes two steps: 1) determine the type of count, and 2) identify counting boundary. It also includes critical logistics around the identification of counting information.
There are three types of counts: development project counts, enhancement project counts and application counts. The development project count also yields the first application count for an application.
Identifying the counting boundary can be complicated. In some cases, changing the counting boundary will make it necessary to do a different type of function point count. For example, what appeared to be a development project count was actually an application count followed by an enhancement project count.
There are three sources for counting information: the system to be counted, its documentation and the system expert (Application domain or solution domain expert). These sources are in increasing order of value to the counting process. One can perform a system count only with access to the system (software): this is usually very time consuming. Counting from the documentation is usually fast if the documentation is complete and easy to understand: It never is! The system expert can walk you through the other information and answer questions as they arise during the count. In function point analysis it is important, to get a system expert assigned with the counter for the entire count. Identification of the appropriate system expert is not always easy. It also depends on the counting boundary. An expert for one component of an application may be unaware of the particulars of other components.
Nevertheless, the system expert is often the application domain expert or the software architect. It may also be an end user who is very familiar with the application. It is usually not the project manager. Interestingly enough, the project manager is usually more willing to work with you directly than to assign the system expert.
B) Do the Count:
1.Count data function types. Data functions are either accessing Internal Logical Files (ILFs) or External Interfaces Files (EIFs). The count of the ILFs and EIFs is done by examining the data model (E/R model or the attributes of the persistent objects in the object model) or by asking the system designer for the application’s main categories of persistent data. This count must be done before the transactions function types are counted, because the complexity of the transactions is dependent on the way the data access functions are identified.
2. Count the transaction function types. Transaction function types are External Inputs (EIs), External Outputs (EOs) or External Queries (EQs). This is typically the longest part of the count, and the part where the system expert's assistance really saves time. Complexity of each transaction is based, in part, on the number of data types it references. The system expert can usually make this determination without consulting any documentation.
3. Compute the Unadjusted function points based on weight factors shown on the next slide.
4.Next we assign rating values 0 to 5 to the so called GSC factors (general system complexity factors). There are 14 GSC factors
shown on the next slide.
5. We sum up all 14 weighted GSC factors and compute the so called valued added factor (VAF). The formula is
VAF = 0.65 + (sum of all GSC factors/100).
6. Next we calculate the Adjusted function points = VAF * Unadjusted function points
7. Then we make a estimation how many function points we can finish per day. This is also called as "Performance factor"･
8. On the basis of the performance factor we calculate the effort in Person Days.

## Slide 23: Function Types
Data function types
  # of internal logical files (ILF)
  # of external interface files (EIF)
Transaction function types
  # of external input (EI)
  # of external output (EO)
  # of external queries (EQ)
Calculate the UFP (unadjusted function points):
UFP = a · EI + b · EO + c · EQ + d · ILF + e · EIF
a-f are weight factors (see next slide)
Notes: There are two ways to count functions. The first way is the traditional Albrecht approach based on the analysis of transactions. The second way is based on the data modeling approach (E/R model).
To do the count, the FP counter has to do the following three steps:
1.Count data function types. Data functions are either accessing Internal Logical Files (ILFs) or External Interfaces Files (EIFs). The count of the ILFs and EIFs is done by examining the data model (E/R model or the attributes of the persistent objects in the object model) or by asking the system designer for the application’s main categories of persistent data. This count must be done before the transactions function types are counted, because the complexity of the transactions is dependent on the way the data access functions are identified.
2. Count the transaction function types. Transaction function types are External Inputs (EIs), External Outputs (EOs) or External Queries (EQs). This is typically the longest part of the count, and the part where the system expert's assistance really saves time. Complexity of each transaction is based, in part, on the number of data types it references. The system expert can usually make this determination without consulting any documentation.
3. Compute the Unadjusted function points based on weight factors shown on the next slide.

## Slide 24: Object Model Example
Customer
Name
Address
Amound Due
Item
Description
Pallets
Value
Storage Date
Owner
Storage Place
Place
Location
Space
owns
Stored at
1
1
*
*

## Slide 25: Mapping Functions to Transaction Types
Add Customer
Change Customer
Delete Customer
Receive payment
Deposit Item
Retrieve Item
Add Place
Change Place Data
Delete Place
Print Customer item list
Print Bill
Print Item List
Query Customer
Query Customer's items
Query Places
Query Stored Items
External Inputs
External Outputs
External Inquiries

## Slide 26: Calculate the Unadjusted Function Points
Weight Factors
Function Type
simple
average
complex
External Input (EI)
x
3
4
6
=
External Output (EO)
x
4
5
7
=
External Queries (EQ)
x
3
4
6
=
Internal Datasets (ILF)
x
7
10
15
=
Interfaces (EIF)
x
5
7
10
=
Unadjusted Function Points (UFP)
=
Number
Notes: After we have counted the ILF,EIF,EI and Eqs, we can compute the unadjusted function points UFP shown on this slide.
In function point analysis, each type of function (input, output, inquiry, file) is first assigned a 'complexity' weighting (simple, average, complex), suggesting that functional size is measured on an ordinal scale.
Next, a specific number of function points are allocated to each function depending on its type and complexity weighting. Within each set of functions belonging to a same type, the allocation of integer values to functions qualifies as an admissible transformation of scale.
The higher the complexity weighting, the more function points are allocated. For instance, external input functions get 3 function points if they are simple, 4 function points if they are of average complexity, and 6 function points if they are complex. Hence, within the class of input functions, one ordinal scale (simple, average, complex) is homomorphically transformed into another ordinal scale (3, 4, 6).
Next, the function points assigned to all individual functions are summed to arrive at the 'unadjusted function point count' for the entire system.
Note, that this operation is not meaningful given the ordinal scale type of the homomorphisms (one per function type) that allocate function point values to functions, but we don’t look into this argument here.

## Slide 27: 14 General System Complexity Factors
The unadjusted function points are adjusted with general system complexity (GSC) factors
GSC1:
Reliable Backup & Recovery
GSC2:
Use of Data Communication
GSC3:
Use of Distributed Computing
GSC4:
Performance
GSC5:
Realization in heavily used configuration
GSC6:
On-line data entry
GSC7:
User Friendliness
GSC8:
On-line data change
GSC9:
Complex user interface
GSC10:
Complex procedures
GSC11:
Reuse
GSC12:
Ease of installation
GSC13:
Use at multiple sites
GSC14:
Adaptability and flexibility
Each of the GSC factors gets a value from 0 to 5.
Notes: There are 14 GSC factors
1. Reliable Backup & Recovery or Operational ease: How effective and/or automated are start-up, back up, and recovery procedures?
2. Data communications: How many communication facilities are there to aid in the transfer or exchange of information with the application or system?
3. Distributed data processing: How are distributed data and processing functions handled?
4. Performance: Did the user require response time or throughput? Transaction rate : How frequently are transactions executed daily, weekly, monthly, etc.?
5. Heavily used configuration: - How heavily used is the current hardware platform where the application will be executed?
6. On-line data entry :- What percentage of the information is entered On-Line?
7. User Friendliness: Was the application designed for end-user efficiency?
8. On-line data change : How many ILF’s are updated by on-line transactions?
9. Complex user interface: Does the user interface require extensive clicks and does it have many data entry fields?
10 Complex procedures: Does the application have extensive logical or mathematical processing?
11. Reusability : Was the application developed to meet one or many userﾕs needs?
12. Ease of Installation: How difficult is conversion and installation?
13. Use at Multiple sites: Was the application specifically designed, developed, and supported to be installed at multiple sites for multiple organizations?
14. Adaptability and flexibility: Was the application specifically designed, developed, and supported to facilitate change?
All the GSC have ratings from 0 to 5.

## Slide 28: Calculate the Effort
After the GSC factors are determined, compute the Value Added Factor (VAF):
Function Points = Unadjusted Function Points * Value Added Factor
  FP = UFP · VAF
Performance factor
  PF = Number of function points that can be completed per day
Effort = FP / PF
VAF = 0.65 + 0.01 * GSCi
i=1
14
GSCi = 0,1,...,5
Notes:   VAF = 0,65 + ((Sum of rated GSC factors)/100) (This means, the result can vary by 35% due to the GSC factors)
The next step is

## Slide 29: Examples
UFP = 18
Sum of GSC factors = 0.22
VAF = 0.87
Adjusted FP = VAF * UFP = 0.87 * 18 ~ 16
PF =2
Effort = 16/2 = 8 person days
UFP = 18
Sum of GSC factors = .70
VAF = 1.35
Adjusted FP = VAF * UFP = 1.35 * 18 ~ 25
PF = 1
Effort = 25/1 = 25 person days
Notes: For example, if the UFP is 18, and VAF is 0.87 the adjusted FP = VAF * UFP = .87 * 18 = 15.9 ~ 16
Now we would know that the complete FP for the application, say a customer GUI, is 16 FP.
As performance factor we choose 2, that is, we say that we will complete 2 FP per day.
Thus the estimate for effort to develop the application would be 8 days.
The VAF and the performance factor can affect the computation of FP quite a bit. So one has to be very careful with this factor.
For example if the VAF is .065+.070 = 1.35
Then we could get FP = 1.32 * 18 =23,76 ~ 24
With PF = 1 the estimated effort would be 24 person days, that is 200 % above the other estimate.

## Slide 30: Advantages of Function Point Analysis
Independent of implementation language and technology
Estimates are based on design specification
  Usually known before implementation tasks are known
Users without technical knowledge can be integrated into the estimation process
  Incorporation of experiences from different organizations
Easy to learn
  Limited time effort
Notes: Function Points measure software size independent of the programming language: no lines of code counting.
Function Points measure functionality by objectively measuring functional requirements.
Function Point Analysis is objective; Function Points are consistent, and Function Points are auditable.
Function Points are independent of technology. Function Points even apply regardless of design.

## Slide 31: Disadvantages of Function Point Analysis
Complete description of functions necessary
  Often not the case in early project stages -> especially in iterative software processes
Only complexity of specification is estimated
  Implementation is often more relevant for estimation
High uncertainty in calculating function points:
  Weight factors are usually deducted from past experiences (environment, used technology and tools may be out-of-date in the current project)
Does not measure the performance of people
Notes: Code reuse and external providers of software components are not considered
Function Points do not measure people directly.
Task planning and controlling is not possible (also: no breakdown to single project phases considered)
Function Points is a macro tool, not a micro tool.

## Slide 32: COCOMO (COnstructive COst MOdel)
Developed by Barry Boehm in 1981
Also called COCOMO I or Basic COCOMO
Top-down approach to estimate cost, effort and schedule of software projects, based on size and complexity of projects
Assumptions:
  Derivability of effort by comparing finished projects (“COCOMO database”)
  System requirements do not change during development
  Exclusion of some efforts (for example administration, training, rollout, integration).

## Slide 33: Calculation of Effort
Estimate number of instructions
  KDSI = “Kilo Delivered Source Instructions”
Determine project complexity parameters: A, B
  Regression analysis, matching project data to equation
3 levels of difficulty that characterize projects
  Simple project (“organic mode”)
  Semi-complex project (“semidetached mode”)
  Complex project (“embedded mode”)
Calculate effort
  Effort = A * KDSIB
Also called Basic COCOMO
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation
(this is how you calibrate your data to the Cocomo model)
But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption:
1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)
Simple: small developer groups work on a well known problem
Semi-complex: complexity between „simple“ and „complex“, either unknown problem or large group of developers
Complex: large groups of developers, Problem domain unknown
[PM] means „person months“
By using cost drivers, in many cases a more accurate estimate is possible

## Slide 34: Calculation of Effort in Basic COCOMO
Formula: Effort = A * KDSIB
  Effort is counted in person months: 152 productive hours (8 hours per day, 19 days/month, less weekends, holidays, etc.)
  A, B are constants based on the complexity of the project
Project Complexity A B
Simple 2.4 1.05
Semi-Complex 3.0 1.12
Complex 3.6 1.20
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation (this is how you calibrate your data to the COCOMO model). But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption: 1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)

## Slide 35: Calculation of Development Time
Basic formula: T = C * EffortD
  T = Time to develop in months
  C, D = constants based on the complexity of the project
  Effort = Effort in person months (see slide before)
Project Complexity C D
Simple 2.5 0.38
Semi-Complex 2.5 0.35
Complex 2.5 0.32

## Slide 36: Basic COCOMO Example
Volume = 30000 LOC = 30KLOC
Project type = Simple
Effort = 2.4 * (30)1.05 = 85 PM
Development Time = 2.5 * (85)0.38 = 13.5 months
=> Avg. staffing: 85/13.5 = 6.3 persons
=> Avg. productivity: 30000/85 = 353 LOC/PM
Compare: Semi-detached: 135 PM 13.9 M 9.7 persons
Embedded: 213 PM 13.9 M 15.3 persons

## Slide 37: Other COCOMO Models
Intermediate COCOMO
  15 cost drivers yielding a multiplicative correction factor
  Basic COCOMO is based on value of 1.00 for each of the cost drivers
Detailed COCOMO
  Multipliers depend on phase: Requirements; System Design; Detailed Design; Code and Unit Test; Integrate & Test; Maintenance

## Slide 38: Steps in Intermediate COCOMO
Basic COCOMO steps:
  Estimate number of instructions
  Determine project complexity parameters: A, B
  Determine level of difficulty that characterizes the project
New step:
  Determine cost drivers
    15 cost drivers c1 , c1 …. c15
Calculate effort
  Effort = A * KDSIB * c1 * c1 …. * c15
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation
(this is how you calibrate your data to the Cocomo model)
But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption:
1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)
Simple: small developer groups work on a well known problem
Semi-complex: complexity between „simple“ and „complex“, either unknown problem or large group of developers
Complex: large groups of developers, Problem domain unknown
[PM] means „person months“
By using cost drivers, in many cases a more accurate estimate is possible

## Slide 39: Calculation of Effort in Intermediate COCOMO
Basic formula:
  Effort = A * KDSIB * c1 * c1 ….* c15
  Effort is measured in PM (person months, 152 productive hours (8 hours per day, 19 days/month, less weekends, holidays, etc.)
  A, B are constants based on the complexity of the project
Project Complexity A B
Simple 2.4 1.05
Semi-Complex 3.0 1.12
Complex 3.6 1.20
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation (this is how you calibrate your data to the COCOMO model). But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption: 1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)

## Slide 40: Intermediate COCOMO: 15 Cost drivers
Product Attributes
  Required reliability
  Database size
  Product complexity
Computer Attributes
  Execution Time constraint
  Main storage constraint
  Virtual Storage volatility
  Turnaround time
Personnel Attributes
  Analyst capability
  Applications experience
  Programmer capability
  Virtual machine experience
  Language experience
Project Attributes
  Use of modern programming practices
  Use of software tools
  Required development schedule
  Rated on a qualitative scale between “very low” and “extra high”
  Associated values are multiplied with each other.

## Slide 41: COCOMO II
Revision of COCOMO I in 1997
Provides three models of increasing detail
  Application Composition Model
    Estimates for prototypes based on GUI builder tools and existing components
  Early Design Model
    Estimates before software architecture is defined
    For system design phase, closest to original COCOMO, uses function points as size estimation
  Post Architecture Model
    Estimates once architecture is defined
    For actual development phase and maintenance; Uses FPs or SLOC as size measure
Estimator selects one of the three models based on current state of the project.

## Slide 42: COCOMO II (cont’d)
Targeted for iterative software lifecycle models
  Boehm’s spiral model
  COCOMO I assumed a waterfall model
    30% design; 30% coding; 40% integration and test
COCOMO II includes new costs drivers to deal with
  Team experience
  Developer skills
  Distributed development
COCOMO II includes new equations for reuse
  Enables build vs. buy trade-offs

## Slide 43: COCOMO II: Added Cost drivers
Development flexibility
Team cohesion
Developed for reuse
Precedent
Architecture & risk resolution
Personnel continuity
Documentation match life cycle needs
Multi-Site development.

## Slide 44: Advantages of COCOMO
Appropriate for a quick, high-level estimation of project costs
Fair results with smaller projects in a well known development environment
  Assumes comparison with past projects is possible
Covers all development activities (from analysis to testing)
Intermediate COCOMO yields good results for projects on which the model is based

## Slide 45: Problems with COCOMO
Judgment requirement to determine the influencing factors and their values
Experience shows that estimation results can deviate from actual effort by a factor of 4
Some important factors are not considered:
  Skills of team members, travel, environmental factors, user interface quality, overhead cost
Notes: Your process may not match up well

## Slide 46: Online Availability of Estimation Tools
Basic and Intermediate COCOMO I (JavaScript)
  http://www1.jsc.nasa.gov/bu2/COCOMO.html
  http://ivs.cs.uni-magdeburg.de/sw-eng/us/java/COCOMO/index.shtml
COCOMO II (Unix, Windows and Java)
  http://sunset.usc.edu/available_tools/index.html
Function Point Calculator (Java)
  http://ivs.cs.uni-magdeburg.de/sw-eng/us/java/fp/

## Slide 47: Additional Readings
B. Boehm, Software Engineering Economics, Prentice-Hall, 1981
B. Boehm, Software Cost Estimation With COCOMO II, Prentice Hall, 2000
D. Garmus, D. Herron, Function Point Analysis: Measurement Practices for Successful Software Projects, Addison-Wesley, 2000
International Function Point Users Group
  http://www.ifpug.org/publications/case.htm
C. Jones, Estimating Software Costs, 1998
S. Whitemire, Object-Oriented Design Measurement, John Wiley, 1997
Notes: B. Boehm, “Software Engineering Economics”, Prentice-Hall, 1981
  Contains an Introduction to COCOMO I
D. Garmus, D. Herron, “Function Point Analysis: Measurement Practices for Successful Software Projects”, Addison-Wesley, 2000
  Overview of Function Point Analysis
S. Whitemire, Object-Oriented Design Measurement, John Wiley, 1997
International Function Point Users Group
  http://www.ifpug.org/publications/case.htm
C. Jones, “Estimating Software Costs”, 1998
  Comprehensive book on software estimation techniques for functionally decomposed systems
From a review of Caspers Jones Book:
“This is one of the most comprehensive books on software estimation techniques and supporting statistics in print. True, this book is deficient in object-oriented estimation, but that gap is filled by the definitive text on that subject, "Object-Oriented Design Measurement" ISBN 0471134171.One thing the author is noted for is backing up assertions with statistics and data. This book is no exception. The full spectrum of estimation techniques is covered in great detail, and the scope of this book starts with background material on estimating, and then addresses all of the major techniques.

## Slide 48: Summary
Estimation is often the basis for the decision to start, plan and manage a project
Estimating software projects is an extremely difficult project management function
If used properly, estimates can be a transparent way to discuss project effort and scope
However,
  Few software organizations have established formal estimation processes
  Existing estimation techniques have lots of possibilities to influence the results - must be used with care.
Notes: Identical estimation technique must be used for all (different) projects
Existing estimation techniques require a post mortem session after the project to improve multipliers
Requires lots of data and experience to develop good multipliers

## Slide 49: Additional Slides

## Slide 50: GSC Factors in Function Point Analysis
Data communications: How many communication facilities aid in the transfer or exchange of information with the system?
Distributed data processing:How are distributed data and processing functions handled?
Performance: Does the user require a specific response time or throughput?
Platform usage: How heavily used is the platform where the application will run?
Transaction rate: How frequently are transactions executed (daily, weekly, monthly)?
On-line data entry: What percentage of the information is entered On-Line?
End-user efficiency: Is the application designed for end-user efficiency?

## Slide 51: GSC Factors in Function Point Analysis (cont’d)
8. On-line update: How many ILF’s are updated on-line?
9. Complex processing: Does the application have extensive logical or mathematical processing?
10. Reusability: Will the application meet one or many user’s needs?
11. Installation ease: How difficult is the conversion and installation?
12. Operational ease: How automated are start-up, backup and recovery procedures?
13. Multiple sites: Will the application be installed at multiple sites for multiple organizations?
14. Adaptability and flexibility: Is the application specifically designed to facilitate change?

## Slide 52: Function Points: Example of a GSC Rating
GSC Value(0-5)
Data communications 1
Distributed data processing 1
Performance 4
Heavily used configuration 0
Transaction rate 1
On-Line data entry 0
End-user efficiency 4
On-Line update 0
Complex processing 0
Reusability 3
Installation ease 4
Operational ease 4
Multiple sites 0
Adaptability and Flexibility 0
Total 22

## Slide 53: Cocomo: Example of Cost Driver Rating
Cost Driver Very Low Low Nominal High Very High Extra High
Required software reliability 0.75 0.88 1.00 1.15 1.40 -
Database size - 0.94 1.00 1.08 1.16 -
Product Complexity 0.70 0.85 1.00 1.15 1.30 1.65
Execution Time Constraint - - 1.00 1.11 1.30 1.66
Main storage constraint - - 1.00 1.06 1.21 1.56
Virtual Storage volatility - 0.87 1.00 1.15 1.30 -
Computer turn around time - 0.87 1.00 1.07 1.15 -
Analyst capability 1.46 1.19 1.00 0.86 0.71 -
Applications experience 1.29 1.13 1.00 0.91 0.82 -
Programmer Capability 1.42 1.17 1.00 0.86 0.70 -
Virtual machine experience 1.21 1.10 1.00 0.90 - -
Prog. language experience 1.14 1.07 1.00 0.95 - -
Use of modern Practices 1.24 1.10 1.00 0.91 0.82 -
Use of software tools 1.24 1.10 1.00 0.91 0.83 -
Required schedule 1.23 1.08 1.00 1.04 1.10 -

## Slide 54: Estimation Technique used in the Exercise
Estimation technique used by Accenture
Uses both top-down and bottom-up elements
Consists of 9 steps:
Determine essential project characteristics
  Infrastructure, technology, team skills, experience…
Use factors for fixed efforts and phases:
  Often derived from already finished phases (step-by-step detailing of estimations)
  Example:
    10% for project management
    10 % for infrastructure
    50% for testing efforts.

## Slide 55: Estimation Technique used in the Exercise
3. Determine work products for the system to be developed (WBS)
5. Determine work product types (use case, user interface, subsystem, …)
4. Assign a complexity factor to each of these work products
6. Define all necessary activities or tasks that need to be done to produce these work products
7. Assign effort estimates (in person days) to these tasks by using past experience
8. Aggregate the estimates to compute the overall project effort
9. Use add-ons (contingency and risk factors)
Notes: Define all necessary activtities or tasks that need to be done to produce these work product types (for example object design, unit testing are tasks to produce a component)

## Slide 56: Example of Complexity and Multipliers (Non-exhaustive)
 | Complexity | Type | Multiplier / Factor | Person Days
Requirements Elicitation |  |  |  | 29
Function A | Low | Use Case | 1 | 5
Function B | Medium | Use Case | 1 | 8
Function C | High | Use Case | 2 | 16
Implementation |  |  |  | 39
Screen A | High | User interface | 1 | 18
Screen B | Low | User interface | 2 | 8
Batch Job A | Medium | Batch | 1 | 8
Batch Job B | Low | Batch | 1 | 5
Software Architecture |  |  | 10 % | 3,9
10% of

## Slide 57: L.W.F Factor