## Slide 1: Configuration & Build Management
Work Breakdown Structures

## Slide 2: Outline of today’s class
Determining Work and Tasks Sizes
Work Breakdown Structure (WBS)
Different Approaches for developing WBSs
Notations for Work Breakdown Structures
Heuristics and examples for WBS
  Starting with templates
  How to identify work
  What do you do with risky tasks?
Using WBS in large projects
  How detailed should a WBS be?
  How can you plan the tasks of a long project when things are unknown or changing all the time?
Notes: Different Approaches are functional or object-oriented, so we have the same dichotomy as in object-oriented vs functional decomposition when modeling systems.

## Slide 3: What is the problem?
Your boss: “How long will this take?”
“As long as I can do it
within 6 months, I keep
my promise.”
You: “Between 1 and 6 months.”
“With hard work, he can
do it in 1 month.”
Notes: Say the following sentences before animating the clouds:
People are not happy when you respond that way.
You figure: Finishing anytime before six months will meet your promise.
Your boss figures: With some hard work he can be done in a month!
In reality, it is often even worse: You don’t have the slightest clue how long it will take, because you don’t know the work to be done!!!
Now add the clouds, and then proceed to the solution: divide and conquer first!

## Slide 4: What is the problem?
Your boss: “How long will this take?”
Solution: Use divide and conquer
  To give a good answer you have to break the work down into activities for which you try to get timing estimates
  Only if you can get good estimates can you compute the estimated project duration.
You: “Between 1 and 6 months.”
“I have not the
slightest clue, if it is
possible at all.”
“Even if it is possible,
I don’t know, how long
it will take.”
Notes: Say the following sentences before animating the clouds:
People are not happy when you respond that way.
You figure: Finishing anytime before six months will meet your promise.
Your boss figures: With some hard work he can be done in a month!
In reality, it is often even worse: You don’t have the slightest clue how long it will take, because you don’t know the work to be done!!!
Now add the clouds, and then proceed to the solution: divide and conquer first!

## Slide 5: Let‘s Build a House
What are the activities that are needed to build a house?

## Slide 6: First Step: Identify the work to be done
Surveying
Excavation
Request Permits
Buy Material
Lay foundation
Build Outside Wall
Install Exterior Plumbing
Install Exterior Electrical
Install Interior Plumbing
Install Interior Electrical
Install Wallboard
Paint Interior
Install Interior Doors
Install Floor
Install Roof
Install Exterior Doors
Paint Exterior
Install Exterior Siding
Buy Pizza
Initially finding these tasks is a brainstorming activity.
Similar to activities used during requirements engineering and analysis
Notes: The similar activity is object and function identification! (here activity identification)
A technique that we learned is Abbot’s technique (no relgious belief, more a technique that can be used when writers block occurs or as a completeness check.

## Slide 7: Second Step: Hierarchically organize the tasks
Building the house consists of
  Prepare the building site
  Building the Exterior
  Building the Interior
Preparing the building site consists of
  Surveying
  Excavation
  Buying of material
  Laying of the foundation
  Requesting permits
Finding this organization involves categorization and refinement.
Good after brainstorming, not during brainstorming

## Slide 8: Third Step: Identify dependencies between tasks
The work breakdown structure does not show any dependence among the activities/tasks
  Can we excavate before getting the permit?
  How much time does the whole project need if I know the individual times?
    What can be done in parallel?
  Are there any critical actitivites, that can slow down the project significantly?
Dependencies like these are shown in the dependency graph
  Nodes are activities
  Lines represent temporal dependencies

## Slide 9: Building a House (Dependency Graph)
START
Request
Survey
ing
Excava
tion
Buy
Material
Founda
tion
Build
Outside
Wall
Install
Exterior
Plumbing
Install
Interior
Plumbing
Install
Exterior
Electrical
Install
Interior
Electrical
Install
Exterior
Siding
Install
Wallboard
Paint
Exterior
Install
Roofing
Install
Flooring
Paint
Interior
Install
Interior
Doors
Install
Exterior
Doors
FINISH
The activity
„Buy Material“ must
Precede the activity
„Lay foundation“
Lay

## Slide 10: Fourth step: Map tasks onto time
Estimate starting times and durations for each of the activities in the dependency graph
Compute the longest path through the graph: This is the estimated duration of your project

## Slide 11: Building a House (Schedule, PERT Chart)
Duration
Start Time
Slack Time
Each Activity has a start time and an estimated duration
START
8/27/94
0
0
Request
Permits
8/27/94
15
0
Survey
ing
8/27/94
3
12
Excava
tion
9/17/94
10
0
Legend
8/29/94
0
Buy
Material
10/1/94
10
0
Lay
Founda
tion
10/15/94
15
0
Build
Outside
Wall
11/5/94
20
0
Install
Exterior
Plumbing
12/3/94
10
12
Install
Interior
Plumbing
12/3/94
12
0
Install
Exterior
Electrical
12/17/94
10
12
Install
Interior
Electrical
12/21/94
15
0
Install
Exterior
Siding
12/31/94
8
12
Install
Wallboard
1/11/95
9
0
Paint
Exterior
1/12/95
5
12
Install
Roofing
1/19/95
9
12
Install
Flooring
1/22/95
18
0
Paint
Interior
1/22/95
11
0
Install
Interior
Doors
2/8/95
7
0
Install
Exterior
Doors
1/19/95
6
15
FINISH
2/16/95
0
0
0

## Slide 12: How do we get good estimate times?
Estimation of starting times and durations is crucial for setting up a plan.
In the lecture on Scheduling we will discuss methods and heuristics on how to do it and how to establish a software project schedule.

## Slide 13: Recall these Definitions
Project:
  A Project has a duration and consists of functions, activities and tasks
Work Package:
  A description of the work to be accomplished in an activity or task
Work Product:
  Any tangible item that results from a project function, activity or task.
Project Baseline:
  A work product that has been formally reviewed and agreed upon.
  A project baselines can only be changed through a formal change procedure
Project Deliverable:
  A work product to be delivered to the customer
Notes: “formally reviewed and agreed upon” does not mean a baseline is frozen! Avoid this term by any means!

## Slide 14: Activities, Tasks and Functions
Activity: A a major unit of work with precise dates that consists of smaller activities or tasks. It culminates in a project milestone.
Task: Smallest unit of work subject to management. Small enough for adequate planning and tracking. Large enough to avoid micro management
Project Function: An activity or set of activities that span the duration of the project

## Slide 15: Tasks
Smallest unit of management accountability
  Atomic unit of planning and tracking
  Tasks have finite duration, need resources, produce tangible result (documents, code)
The description of a task is done in a work package
  Name, description of work to be done
  Preconditions for starting, duration, required resources
    Other work packages that need to be completed before this task can be started.
  Work products to be produced, acceptance criteria for it
  Risk involved
Completion criteria
  Includes the acceptance criteria for the work products (deliverables) produced by the task.

## Slide 16: Determining Task Sizes
Finding the appropriate task size is problematic
  Todo lists and templates from previous projects
  During initial planning a task is necessarily large
  You may not know how to decompose the problem into tasks at first
  Each software development activitity identifies more tasks and modifies existing ones
Tasks must be decomposed into sizes that allow monitoring
  Depends on nature of work and how well task is understood.
  Work package usually corresponds to well defined work assignment for one worker for a week or two.
  Work assignments are also called action items

## Slide 17: Work Breakdown Structure
*
Task
*
Work
Activity
Work Breakdown Structure
Work Breakdown Structure: The aggregation of all the work
to be performed in a project. Often called WBS

## Slide 18: Approaches to Develop Work Breakdown Structures
Product component approach
  Structure the work based on the work products
  Examples: Design documents, manuals, the delivered system,…
Functional approach
  Structure the work based on development activities and project functions
  Examples: Analysis, design, implementation, integration,…
Geographical area approach
Structure the work based on the geographical location
Examples: Munich team,Pittsburgh team, off-shore team,…
Organizational approach
Structure the work based on the organizational structure
Example: R&D department, predevelopment, product development, marketing, sales,…
Notes: There are several different approaches to develop and display a work breakdown structure.
Each is effective under different circumstances
Approaches to break activities into detail by

## Slide 19: When to use what Approach
The teams are distributed over the continent:
  Geographical area approach
The teams consist of experienced developers:
  Product component approach
The project has mostly beginners or an unexperienced project manager:
  Functional approach
The project is a continuation of a previously successful project, there are no changes in the requirements and no new technology enablers
  Organizational approach
Whatever approach you choose, stick with it to prevent possible overlap in categories
Notes: At the end of this slide: “If you don’t stick with the approach, your workbreakdown structure will lead to double work and unmanageable tasks (tasks that are managed by more than one person: The geographical boss and the product manager, for example. “

## Slide 20: Mixing different Approaches is bad
Consider the WBS for an activity „Prepare report“
Functional approach:
  Write draft report
  Have draft report reviewed
  Write final report
Product component approach:
  Chapter 1
  Chapter 2
  Chapter 3
Mixed approach:
  Chapter 1
  Chapter 2
  Chapter 3
  Have draft report reviewed
  Write final report
Why is this bad?
Notes: Answer to question at the end of the slide:
“Prepare the final version of Chapter 3” can be included in either in the task: “Chapter 3” or in the task “Write final report”

## Slide 21: How do you develop a good WBS?
Top down approach:
  Start at the highest, top level activities and systematically develop increasing levels of detail for all activities.
Bottom up approach (“Brainstorming”):
  Generate all activities you can think of that will have to be done and then group them into categories.
Which one you use depends on
  how familiar you and your team are with the project,
  whether similar projects have successfully been performed in the past, and
  how many new methods and technologies will be used.
Notes: Break
Example for previous slide: You are at the beach, you are building a sandcastl e, somebody else too, soon you are noticing that the wall, your wall!, is used by the oterh kid. War! Sandwar! This type of war is typical, if you mix approaches, for example if you mix the functional WBS with the product component approach.

## Slide 22: The Top Down WBS Development
Specify all activities required for the entire project to be finished
Determine all tasks required to complete each activity
If necessary, specify sub-activities required to complete each task
Continue in this way until you have adequately detailed your project.
Top Down WBS Approach is good if
  You are familiar with the problem (or your team)
  You have successfully managed a similar project in the past
  You are not introducing new methodologies, methods or tools

## Slide 23: The Brainstorming WBS Development
On a single list, write any activities you think will have to be performed for your project.
Brainstorming means you
  Don’t worry about overlap or level of detail
  Don’t discuss activity wordings or other details
  Don’t make any judgements
  Write everything down
Then study the list and group activities into a few major categories with common characteristics
If appropriate, group identified activities into higher level activities
Consider each category you have created and use the top-down WBS development to determine any additional activities you may have overlooked.

## Slide 24: Displaying Work Breakdown Structures
Three different formats are usually used:
Organization-chart format
  Effectively portrays an overview of your project and the hierarchical relationships of different activities and tasks.
Outline format
  Subactivities and tasks are indented
Bubble format
  The bubble in the center represents your project
  Lines from the center bubble lead to activities
  Lines from activities lead to tasks

## Slide 25
Prepare Report
1.0 Prepare draft report
2.0 Review draft report
3.0 Prepare final report
  3.1 Write final report
  3.2 Print final report
Review
Draft Report
Prepare
Report
Review
Draft Report
Review
Final Report
Print
Final Report
Write
Final Report
Prepare Report
Prepare
Draft Report
Review
Draft Report
Prepare
Final Report
Write
Final Report
Print
Final Report
Org-Chart Format
Outline Format
Bubble Format

## Slide 26: What is the best display format for WBS?
Organization-chart format:
  Often good for a “bird view” of the project (executive summaries,...)
  Less effective for displaying large numbers of activities
Outline format:
  Easier to read and understand if WBS contains many activities
Bubble format:
  Effective for supporting brainstorming
  Not so good for displaying work breakdown structures to audiences who are not familiar with the project.
In large projects:
  Use bubble format to develop the WBS, then turn it into Organization-chart or Outline format.
  Display activities in Organization-chart format,
  Display subactivities and tasks in Outline format

## Slide 27: Heuristics for developing high quality WBS
Involve the people who will be doing the work in the development of the WBS
  In particular involve the developers
Review and include information from work breakdown structures that were developed for similar projects
  Use a project template if possible
Use more than one WBS approach
  Do project component and functional approach simultaneously.
  This allows you often to identify overlooked activities
Make assumptions regarding uncertain activities
  Identify risky activities
  These are often the activities whose times are hard to estimate
Notes: Question: using more than one WBS approach? Did we not just say a few moments ago, that it is not good to use more than one approach? Notice the difference between developing a WBS and using it for tracking a project.
Large projects: Keep your current work breakdown structure current, update your WBS regularly

## Slide 28: Choose a single WBS Approach
Develop the WBS with different approaches. This is good, because it allows you to identify activities that you may overlook otherwise
Choose a single WBS approach to be used in the SPMP and for your project:
  Nothing confuses people fast than trying to use two different work breakdown structures to describe the same project.
Notes: However, after you identify these activities add them to one WBS approach

## Slide 29: How Detailed should the WBS be?
Sometimes the activities are not clear at all, especially in software projects, because of:
  Unclear requirements and/or changing requirements
  Dependency on technology enablers that are promised to appear after project kickoff
  Simultaneous development of hardware and software (“concurrent engineering”)
Heuristic: A project plan, especially for an innovative software project, should not address details beyond 3 months.
  Even for the first 3 months project activities might not all be detailable, for example when the requirements are unclear or change or introduction of technology enablers is expected.
How should we describe a WBS for a longer project?

## Slide 30: Doing a WBS for Long-Term Projects
Developing a WBS for a long project (longer than 3 months), use at least two phases
Phase 1 (3 months): Plan your WBS in detail
  List all activities that take 2 weeks or less to complete
Phase 2, Phase 3, … (3-months) Plan your WBS for these phases in less detail
  List activities that take between 1 and 2 months
At the end of phase 1, revise the activities planned for phase 2 and plan them on the two week level for the next 3 months
  Modify future activities based on the results of your work so far
Revise the SPMP throughout the project
  Remember: The SPMP is an “evolving” document just like the RAD and SDD.

## Slide 31: Phases and large Projects
Project-Initiation Phase
Steady State Phase
  Initial Planning phase
Project-Termination Phase

## Slide 32: Project-Initiation Phase: To-Do List
Meet with client, develop problem statement
Develop top level design: System as a set of subsystems
Establish staffing plan (flat staffing, ramping up)
Identify human resources: existing and new employees
Hire team members
Assign each subsystem to a single team. Establish cross-functional teams (architecture, documentation, demo)
Write problem statement (with client and other stake holders; if possible, involve project participants early)
Write initial SPMP with WBS without schedule and budget
  - Get this project plan approved by client
  Hand out 2 documents at project kickoff:
    Problem statement and SPMP
Activities:
  Duration of project-initiation-phase: 2-4 weeks
When? Before project kickoff
Notes: Fred Brooks, The mythical months

## Slide 33: Phases and large Projects
Project-Initiation Phase
Steady State Phase
  Initial Planning phase
Project-Termination Phase

## Slide 34: Initial Planning Phase: To-Do List
Activities
  Do scouting on technology enablers that might influence the design or nonfunctional requirements
  Revise requirements and initial top level design if necessary
  Revise team structure, reassign team members if necessary
  Revise WBS and dependencies
  Establish cost and scheduling information
  Agree with client on requirements, duration and cost of the project
  Write the “project agreement” (companion document to the SPMP)
Duration: About 2 weeks
When: After project kickoff, this is often called the “planning phase”, parallel to “requirements elicitation phase”.
Notes: The scouting is often called innovation management
The project agreement should not be written too early. Good heuristics: After a first analysis of the requirements, ideally after the requirements analysis phase.

## Slide 35: Project-Termination Phase
Do a project-review
  “What went right, what went wrong”
  Often called project post-mortem review
Based on input from the post-mortem review
  Review your software process, identify any new activities that happened in the project
  Review your project kickoff activities
  Review your SPMP template (to be reused for your next project).

## Slide 36: Summary
Different approaches to develop a WBS
  Product Approach
  Functional Approach
  Geographical Approach
  Organizational Approach
Top down and bottom up WBS development
Heuristics for developing good WBS
WBS for Large Projects

## Slide 37: Backup Slides

## Slide 38: Heuristic: Use Templates
Try to derive the SPMP from a template
  The template should reflect the cumulative experience you have gained from the projects of a particular type.
  Using templates saves you time, and may improve your accuracy
When developing templates, develop them for frequently performed tasks
  Reviews, meetings (agendas and protocols), presentations
Develop checklists:
  Develop and modify your WBS templates from previous projects that worked, not from plans that looked good.
  Use templates as starting points, not as ending points
  Continually update your templates to reflect the experience gained from performing different projects.

## Slide 39: Heuristic: Develop more than one WBS
Create several different hierarchies with different categories for your work breakdown structure
  Having two or more different perspectives helps you to identify activities you may overlook otherwise
Good starting point are:
  Entity-oriented decomposition
  Activity-oriented decomposition
Example: You are running your first object-oriented project
  Develop a WBS based on the project documents
  Develop a WBS based on the software process activities.

## Slide 40: Heuristic: Identifying Risky Activities
When you identify activities for the WBS, you can also identify the risks in your project
Risks are associated with unknown information
  “Known unknown”: Information you don’t have but someone else does
    Identify the information holder, determine the information (Interviews, Phone calls, tasks analysis)
  “Unknown unknown”: Information you don’t have because it does not yet exist
    Describe the risks in the SPMP and develop contingency plans
    Follow these contingency plans when you find out the information does not exist.

## Slide 41: Risks and Contingency Plan Examples
Risk: Members in key roles leave the project
  Contingency Plan: Roles are assigned to somebody else. Functionality of the system is renegotiated with the client
Risk: The project is falling behind schedule.
  Contingency Plan: Schedule extra project meetings
Risk: Team 1 cannot provide functions needed by team 2
  Contingency Plan A: Drop the functionality
  Contingency Plan B: The liaisons of both teams get together to solve this problem
Risk: The planned iPhone will not be available
  Contingency Plan: We will use Android instead.

## Slide 42: Risks and Contingency Plan Examples ctd
Risk: The selection of the database system takes too much time
  Contingency Plan: The database team uses a bridge pattern and provides a test stub to be used by the other teams for data access while the selection process goes on
Risk: The customer is not available for reviewing the user interface during development
  Contingency Plan: Make the design decisions that we feel are appropriate
Risk: No suitable wireless library can be found
  Contingency Plan: The wireless team develops its own library.

## Slide 43: WBS Based on Project Documents (Entity-oriented)
<<Name>>
Project
Problem
Statement
Project
Agreement
RAD
- Write Introduction
- Write Requirements
Write Constraints
- Write Introduction
- Describe Functional Model
- Describe Object Model
Describe Dynamic Model
- Write Requirements
- Write Constraints
- Write Acceptance Criteria
- Promise delivery date
SDD
- Write Design Goals
- Write Hardware/ Software mapping
- Write Boundary Conditions
Write Data Management

## Slide 44: WBS Based on Software Process (Activity-oriented)
<<Name>>
Project
Project
Initiation
Planning
Analysis
- Establish guidelines
- Formulate requirements with client
- Establish scenarios
- Write project agreement
- Brainstorm about application domain objects
- Develop class diagram
- Partition objects into boundary, entity and control objects
Develop use cases
- Write RAD
- Determine WBS
- Determine dependencies between tasks
- Write SPMP
- Assign teams to subsystems
- Establish project calendar
Design
- Develop Models
- Write code
- Present problems to coach
- Give status reports
- Write SDD
- Write ODD
Question: Which activities mentioned in the WBS based on Project Documents are left out in the WBS based on Software Process?

## Slide 45: Estimates for establishing WBS
Establishing an WBS in terms of percentage of total effort:
  Small project (7 person-month): at least 7% or 0.5 Person Months (PM)
  Medium project (300 person-month): at least 1% or 3 PMs
  Large project (7000 person-month): at least 0.2 % or 15 PMs
  Source: Barry Boehm, Software Economics ( a little bit out of date)