## Slide 1: Scheduling
Software Engineering II
Project Organization &
Management

## Slide 2: Where are we?
Work Breakdown Structures
Estimation
Scheduling
✔
✔
today

## Slide 3: Managing Complexity
Technical Side | Managerial Side
Using proven strategies:
  Divide & Conquer
  Minimize coupling
  Maximize coherence
Work Breakdown Structure
(functional, object-oriented, geographical)
Identification of Time as an important Attribute
Dependencies
(aggregation, successive/parallel tasks)
Object Identification
Identification of Attributes
Identification of Associations (aggregation, inheritance)
Problem decomposition
(Service identification (func.), Modularization (struct.) and Architecture (subsys. decomp.)
Identification of Tasks
Notes: Associations: Structural Associations – Model Constraints

## Slide 4: Managing Change
Change influences management aspects as much as technical aspects.
Technical Side | Managerial Side
Release Management and Roadmapping
Incremental Planning/Estimation
Iterative Planning/Estimation
(Cone of uncertainty [Boehm 1981])
Software Configuration Management
Incremental Development
Iterative Software-Lifecycles

## Slide 5: Cone of uncertainty [Boehm 1981]
Therefore multiple estimations are needed:
  At the beginning
  After system design
  After detailed design

## Slide 6
Camp III
Camp II
Camp I
Summit of Denali (Mt. McKinley)
Camp I
Cassin
Ridge
West Rib
Notes: When you want to climb McKinley, you have several alternatives:
West Rib: Takes 3 camps for normal climbers, 50-55 degrees at the crux
Second hardest route, but can be done by good climbers in 4 days
Cassin: can be done with one Camp, duration 2 days, hard climbing, the hardest route , only for very good climbers
The West Rib climb can be broken down into 5 tasks: Climb to Camp1, climb to Camp2, Climb to Camp 3, Climb to Summit, climb back to Base camp. Duration: 4 days to summit, 1 day back to base camp (not shown, but definitely a must do task:-)
The summit via the Cassin ridge can be done in 2 days (again for mere mortals), so the cassin route back to base camp can be done in 2 days.
2 days is shorter than 5 days. Which route should we do? Should you do the Cassin because it can be done in 12 days?
Maybe none of these, but the normal route, the west buttress route?
BTW, the exceptional Russian climber did the West Rib solo in 10 hours!

## Slide 7: Outline
Preconditions: WBS and Estimates
Dependency diagrams
Determining times of activities
Determining critical path and slack times
Determining project duration
Scheduling Heuristics
  How to live with a given deadline
  Optimizing schedules
  Rearranging schedules
Notes: The last lectures dealt with Work Breakdown Structures, Estimation, Organization.
Today we focus on Scheduling. In particular, we will look at techniques that allow us to determine the schedule when we have estimated times for tasks.

## Slide 8: Why Dependency Diagrams?
Example:
  A project consists of 5 tasks; each of these takes one week to complete.
  How long does the project take?
Example:
  A project consists of 5 tasks. Task 1 has to be finished before any other tasks can start. Task 2 and task 3 can be done in parallel, task 4 and 5 cannot. Task 4 and 5 both depend on task 2.
  Can the project be finished in 3 weeks, if each of the tasks takes a week to complete?
  What if 4 and 5 could be done in parallel and 2 and 3 could not?
Dependency Diagrams are a formal notation to help in the construction and analysis of complex schedules
Notes: When activity dependencies become complex, you cannot to compute the schedule in
your head any more.
Duration of first example project: 1 week.
Duration of second example project: not possible in 3 weeks

## Slide 9: Dependency Diagrams (Overview)
Dependency diagrams consist of three elements
  Event: A significant occurrence in the life of a project.
  Activity: Amount of work required to move from one event to the next.
  Span time: The actual calendar time required to complete an activity.
    Span time parameters: availability of resources, parallelizability of the activity
Dependency diagrams are drawn as a connected graph of nodes and arrows. Two commonly used notations to display dependency diagrams are:
  Activity-on-the-arrow
  Activity-in-the-node
Notes:   Activity-on-the-arrow => Mealy automaton
  Activity-in-the-node => Moore automaton
  Event is often called milestone
  Span time is also called duration or elapsed time.

## Slide 10: The Polaris Missile Project
The project started in 1956
Its goal was to develop a submarine-launched, two-stage solid-fuel nuclear-armed ballistic missile (SLBM) as replacement for the Regulus cruise missile
Because of the high uncertainty of the project (research and development of completely new parts – lots of contractors) a new project management technique was needed.

## Slide 11: PERT
PERT stands for “Program Evaluation and Review Technique”
PERT uses an activity-on-the-arrow notation
Algorithm:
  Assign optimistic, pessimistic and most likely estimates for the span times of each activity.
  Compute the probability that the project duration will fall within specified limits.
  At first the method did not take cost into consideration but was later extended to cover cost as well.
  Still more fitting for projects where duration matters more than cost.

## Slide 12: 1) Activity-on-the-arrow Diagram Notation
A
B
t
Event (Milestone
or Deliverable)
Event (Milestone
or Deliverable)
Activity
t = 4 weeks
Analysis Review
Design Review
System Design
Span Time

## Slide 13: 2) Activity-in-the-node Diagram Notation
RAD
available
t = 0
System Design
t = 2 weeks
SDD
available
t = 0
Event (Milestone
or Deliverable)
Event (Milestone
or Deliverable)
Activity
A Node is either an activity or an event.
Distinction: Events have span time 0
A
B
C
Milestone boxes are often highlighted by double-lines
A
tA = 0
B
tB = 2
C
tC = 0

## Slide 14: Example of an Activity-in -the -Node Diagram
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
5 = 2

## Slide 15: What do we do with these diagrams?
Compute the project duration
Determine activities that are critical to ensure a timely delivery
Analyze the diagrams
  To find ways to shorten the project duration
  To find ways to do activities in parallel
2 techniques are used
  Forward pass (determine critical path)
  Backward pass (determine slack time)
Notes: The critical path is the sequence of activities that take the longest time to complete. Let’s take a more precise look, let’s define critical path and slack time

## Slide 16: Definitions: Critical Path and Slack Time
Critical path:
  A sequence of activities that take the longest time to complete
  The length of the critical path(s) defines how long your project will take to complete.
Noncritical path:
  A sequence of activities that you can delay and still finish the project in the shortest time possible.
Slack time:
  The maximum amount of time that you can delay an activity and still finish your project in the shortest time possible.

## Slide 17: Example of a critical path
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
5 = 2
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
Critical path with bold and red arrows

## Slide 18: Analyzing Dependency Graphs
Determination of critical paths
Determination of slack times

## Slide 19: Analyzing Dependency Graphs
Determination of critical paths
  Compute earliest start and finish dates for each activity
  Start at the beginning of the project and determine how fast you can complete the activities along each path until you reach the final project milestone.
  Also called forward path analysis
Determination of slack times
  Start at the end of your project, figure out for each activity how late it can be started so that you still finish the project at the earliest possible date.
  Also called back path analysis
Notes: Forward Path -> Proactive
Back Path -> Lazy

## Slide 20: Definitions: Start and Finish Dates
Earliest start date (ES):
  The earliest date you can start an activity
Earliest finish date (EF):
  The earliest date you can finish an activity
Latest start date (LS):
  The latest date you can start an activity and still finish the project in the shortest time
Latest finish date (LF):
  The latest date you can finish an activity and still finish the project in the shortest time.

## Slide 21: Computing Start and Finish Times
To compute start and finish times, we apply two rules
  Rule 1: After a node is finished, we can proceed to the next node(s) that is (are) reachable via a transition from the current node.
  Rule 2: To start a node, all nodes from which transitions to that node are possible must be complete.

## Slide 22: Summary: Analyzing Dependency Diagrams
Forward pass: Goal is the determination of critical paths
  Compute earliest start and finish dates for each activity
Backward pass: Goal is the determination of slack times
  Compute latest start and finish dates for each activity
Rules for computing start and finish times
  Rule 1: After a node is finished, proceed to the next node that is reachable via a transition from the current node.
  Rule 2: To start a node all nodes from which transitions to that node are possible must be complete.
Notes: Forward pass: Goal is the determination of critical paths
  Compute earliest start and finish dates for each activity
  Start at the beginning of the project and determine how fast you can complete the activities along each path until you reach the final project milestone.
Backward pass: Goal the determination of slack times
  Compute latest start and finish dates activity
  Start at the end of your project, figure out for each activity how late it can be started so that you still finish the project at the earliest possible date.
Rules for computing start and finish times
  Rule 1: After a node is finished, proceed to the next node that is reachable via a transition from the current node.
  Rule 2: To start a node all nodes must be complete from which transitions to that node are possible.

## Slide 23: Forward Path Analysis
Activity Earliest Start (ES) Earliest Finish (EF)
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
A1 Start of week 1 End of week 5
A2 Start of week 6 End of week 6
A3 Start of week 1 End of week 1
A5 Start of week 6 End of week 7
A4 Start of week 2 End of week 4
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Project Duration = 7

## Slide 24: Backward Path Analysis
Activity Latest Start (LS) Latest Finish (LF)
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
A2 End of week 7
A3 End of week 2
A5 End of week 7
A1 End of week 5
A4 End of week 5
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start of week 6
Project Duration = 7
Start of week 3
Start of week 1
Start of week 7
Start of week 2
Notes: Now we have the project duration, we can determine the latest start and finish times

## Slide 25: Computation of slack times
Slack time ST of an activity A:
  STA = LSA - ESA
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
Activity 4
t4 = 3
Activity 2
t2 = 1
Activity
A1
A2
A3
A4
A5
Slack time
0
1
1
1
0
Slack times on the same path influence each other.
Example: When activity 3 is delayed by one week, activity 4 slack time becomes zero weeks.
STA4 = 3 - 2 = 1
Example: STA4 = ?
Notes: With the results of the forward and backward analysis we can determine the slack times
STA = LSA-ESA Subtract the earliest start date from the latest start date for each activity

## Slide 26: Path types in dependency graphs
Critical path: Any path in a dependency diagram, in which all activities have zero slack time.
Noncritical path: Any path with at least one activity that has a nonzero slack time.
Overcritical path: A path with at least one activity that has a negative slack time.
  Overcritical paths should be considered as serious warnings: Your plan contains unrealistic time estimates

## Slide 27: Path types in dependency graphs cont.
Any dependency diagram with no fixed intermediate milestones has at least one critical path.
A project schedule with fixed intermediate milestones might not have a critical path
  Example:
    The analysis review must be done 1 month after project start
    The estimated time for all activities before the review is less than 4 weeks.

## Slide 28: Types of Dependencies (Examples taken from Microsoft Project)
Finish-to-start (FS) Task (B) cannot start until task (A) finishes. For example, if you have two tasks, "Construct fence" and "Paint fence," "Paint fence" can't start until "Construct fence" finishes. This is the most common type of dependency.
Start-to-start (SS) Task (B) cannot start until task (A) starts. For example, if you have two tasks, "Pour foundation" and "Level concrete," "Level concrete" can't begin until "Pour foundation" begins.
Finish-to-finish (FF) Task (B) cannot finish until task (A) finishes. For example, if you have two tasks, "Add wiring" and "Inspect electrical," "Inspect electrical" can't finish until "Add wiring" finishes.
Start-to-finish (SF) Task (B) cannot finish until task (A) starts. This dependency type can be used for just-in-time scheduling up to a milestone.

## Slide 29: Dependency constraints
As Soon As Possible (ASAP) – Flexible Schedule the task as soon as possible without any other restrictions.
Start No Earlier Than (SNET) – Moderate Specify the earliest date for a task to start. The task cannot start before that date.
Start No Later Than (SNLT) – Moderate Specify the latest possible date for a task to begin. The task cannot be pushed to start after that date.
Must Start On (MSO) – Inflexible The task must start on that exact date.
As Late As Possible (ALAP) – Flexible Schedule the task as late as possible without any other restrictions.
Finish No Earlier Than (FNET) – Moderate Specify the earliest date for a task to end. The task cannot end before that date.
Finish No Later Than (FNLT) – Moderate Specify the latest possible date for a task to end. The task cannot be pushed to end after that date.
Must Finish On (MFO) – Inflexible The task must finish on that exact date.

## Slide 30: Frequently used formats for schedules
Milestone View:
  A table that lists milestones and the dates on which you plan to reach them.
Activities View:
  A table that lists the activities and the dates on which you plan to start and end them
Gantt chart View:
  A graphical view illustrating on a timeline when each activity will start, be performed and end.
Combined Gantt Chart and Milestone View:
  The Gantt Chart contains activities as well as milestones.
PERT Chart View:
  A graphical representation of task dependencies and times.
Burndown Chart View:
  A graph showing the number of open tasks over time.
Notes: Milestone View is also often called the “Key-Events report”:

## Slide 31: Milestone View (Key-Events Report)
Date Milestone
August 26 Project Kickoff (with Client)
October 16 Analysis Review
October 26 System Design Review
November 7 Internal Object Design Review
November 20 Project Review (with Client)
November 26 Internal Project Review
December 11 Acceptance Test (with Client)
Good for introduction of project
and high executive briefings

## Slide 32: Activities View
Date Project Phases
Jul 17 - Aug 23 Preplanning Phase
Aug 26 - Sep 24 Project Planning
Sep 11 - Oct 8 Requirements Analysis
Oct 9 - Oct 26 System Design
Oct 28 - Nov 7 Object Design
Nov 8 - Nov 20 Implementation & Unit Testing
Nov 22 - Dec 4 System Integration Testing
Dec 4 - Dec 10 System Testing
Dec 11- Dec 18 Post-Mortem Phase
Good for documentation and
during developer meetings

## Slide 33: Gantt Chart
Activity 1
Activity 2
1
2
3
4
5
6
7
0
Activity 3
Activity 4
Activity 5
Easy to read
Time (in weeks after start)

## Slide 34: Gantt Chart
Time (in weeks after start)
Activity 1
Activity 2
1
2
3
4
5
6
7
0
Activity 3
Activity 4
Activity 5
Project Start
Project Finish
with milestones
  Good for reviews
Design Review

## Slide 35: Two Types of Gantt Charts
Person-Centered View
  To determine people‘s work load
Activity-Centered View
  To identify teams working together on the same tasks
Time
Joe, Toby
A1
A2
A3
Joe
Clara, Toby, Joe
Time
Joe
Mary
Toby
Clara
A1
A3
A1
A3
A2
A3
Notes: Joe has the most to do. The manager should probably assign one of Joes tasks to Mary

## Slide 36: PERT Chart
  Good overview of task dependencies
Notes: Joe has the most to do. The manager should probably assign one of Joes tasks to Mary

## Slide 37: Burndown Chart
  Good for project controlling
Notes: Joe has the most to do. The manager should probably assign one of Joes tasks to Mary

## Slide 38: Which view should you use?
Milestone View:
  Good for introduction of project and high executive briefings
Activity View:
  Good for developer meetings
Gantt Chart Views: Base the view on the WBS structure and on the experience of the participants:
  Managing experienced teams - use a person-centered view
  Managing beginners - use an activity oriented view
PERT Chart View:
  Good for clear illustration of task dependencies.
Burndown Chart View:
  Good for progress reports, project controlling.
Notes: In General : Choose one view, stay with it.

## Slide 39: Developing a Schedule for Integration Testing
Five Steps:
  1. Start with System Decomposition
  2. Determine your Integration Testing Strategy
  3. Determine the Dependency Diagram
  4. Add Time Estimates
  5. Visualize the activities on a time scale: Gantt Chart

## Slide 40: 1. Start with System Decomposition

## Slide 41: 2. Determine the Integration Testing Strategy
There are many integration testing strategies
We choose sandwich testing
Sandwich testing requires 3 layers
  Reformulate the system decomposition into 3 layers if necessary
Identification of the 3 layers and their components in our example
  Top layer: A
  Target layer: B, C, D
  Bottom layer: E, F, G
Notes: We choose sandwich testing. Why?
  It allows many parallel testing activities, possibly shortening testing time

## Slide 42: 3. Determine the Dependency Diagram (UML Activity Diagram)
Target layer components: B, C, D

## Slide 43: Modified Sandwich Testing Strategy

## Slide 44: 4. Add Time Estimates (PERT Chart)

## Slide 45: 5. Visualize your Schedule (Gantt Chart View )

## Slide 46: Tools support
Microsoft Project: PERT, Gantt, Milestone/Gantt Charts
  Windows
  Demo: http://www.microsoft.com/office/project
Fast Track: Gantt Charts
  Multiplatform: Windows, MacOS X, Palm
  Demo: http://www.aecsoftware.com/
Shared Plan: PERT, Gantt, Milestone/Gantt Charts
  Multiplatform: Windows, MacOS X, Linux
  Compatible with Microsoft Project
  Demo: http://www.sharedplan.com/
Merlin: Gantt Charts, Mindmaps
  MacOS X
  Demo: http://www.novamind.com/merlin/
Notes: Many products available. Examples
Tool support for
  Graphical user interface for entering activity data
  Automatic computation of critical paths
  Multiple views (PERT, Gantt, table views) and switching between these views
  Tool use and training beyond the scope of this class

## Slide 47: Scheduling Heuristics
How to develop an initial project schedule
How to shorten the project duration
Mistakes made during preparation of schedules
The danger of fudge factors
How to identify when a project goes off-track (actual project does not match the project plan).
How to become a good software project manager

## Slide 48: How to develop an Initial Project Schedule
Identify all your activities
Identify intermediate and final dates that must be met
Assign milestones to these dates
Identify all activities and milestones outside your project that may affect your project’s schedule
Identify “depends on” relationships between the activities
Draw a dependency diagram for the activities and relationships
Determine critical paths and slack times of noncritical paths.
Notes: Identify all your activities (reuse a template if possible)
Transition to next slide: As an example, we show how to establish a schedule for system integration testing
  From: Bruegge&Dutoit 2003, Chapter 9 Testing

## Slide 49: Reducing the planned project time
Recheck the original span time estimates
  Ask other experts to check the estimates
  Has the development environment changed? (batch vs. interactive systems, desktop vs. laptop development)
Consider different strategies to perform the activities
  Consider to Buy a work product instead of building it (Trade-off: Buy-vs.-build)
  Consider extern subcontractor instead of performing the work work internally

## Slide 50: Reducing the planned project time (2)
Hire more experienced personnel to perform the activities
  Trade-off: Experts work fast, but cost more
Try to find parallelizable activities on the critical path
  Continue coding while waiting for the results of a review
  Risky activity, portions of the work may have to be redone.
Develop an entirely new strategy to solve the problem

## Slide 51: Mistakes when Developing Schedules
The „Backing in“ Mistake
Using Fudge Factors
Notes: Typical Mistakes when Developing Schedules

## Slide 52: The “Backing in” Mistake
Definition “Backing In”:
  You start at the last milestone of the project and work your way back toward the starting milestone, while estimating durations that will add up to the amount of the available time
Problems with Backing in:
  You probably miss activities because your focus is on meeting the time constraints rather than identifying the required work
  Your span time estimates are based on what you allow activities to take, not what they actually require
  The order in which you propose activities may not be the most effective one.
Instead, start with computing all the required times and then try to shorten the project duration

## Slide 53: Using Fudge Factors
Fudge factor:
  A fudge factor is the extra amount of time you add to your best estimate of span time “just to be safe”.
  Example: Many software companies double their span time estimates.
Don’t use fudge factors!
  If an activity takes 2 weeks, but you add a 50% fudge factor, chances are almost zero that it will be done in less then 3 weeks.
  Reason: Parkinson’s law
Notes: Parkinson formulated this law for project completion:
  Work tends to expand to fill the time allotted for it.
To deal with this phenomen, an experienced project manager introduces a fudge factor.

## Slide 54: Heuristics for dealing with Time
1. First set the Project Start Time =>
  Determines the planned project time
  Determine the critical path(s)
2. Then try to reduce the planned project time
  If you want to get your project done in less time, you need to consider ways to shorten the aggregate time it takes to complete the critical path.
Avoid fudge factors

## Slide 55: Identifying when a Project goes Off-Track
Determine what went wrong: Why is your project got off track?
  Behind schedule
  Overspending of resource budgets
  Not producing the desired deliverables
Identify the reasons
Notes: Identify the Reason(s):
  You are new on the job, this is your first project, and you made mistakes
  Key people left the teams or new ones are joining it
  Key people lost interest or new ones entered the picture
  The requirements have changed
  New technology has emerged
  The business objectives have changed
  Organizational priorities have shifted (for example after a merger)

## Slide 56: Heuristics to get a Project back on Track
Reaffirm your plan
  Reaffirm your key people
  Reaffirm your project objectives
  Reaffirm the activities remaining to be done
  Reaffirm roles and responsibilities
Refocus team direction and commitment
  Revise estimates, develop a viable schedule
  Modify your personnel assignments
  Hold a mid-project kickoff session
  Closely monitor and control performance for the remainder of the project
Get practical experience

## Slide 57: Become a better Software Project Manager
End User and Management involvement 35%
  Learn how to involve the customer and end users
  Learn how to get support from your upper management
Practice project management 30 %
  Do as many projects as possible
  Learn from your project failures
Focus on objectives and requirements 20%
  Distinguish between core, optional and fancy requirements
Notes: Focus on business objectives and requirements

## Slide 58: How to become a better project manager
Don’t assume anything
  Find out the facts.
  Use assumptions only as a last resort.
  With every assumption comes a risk that you are wrong.
Communicate clearly with your people.
  Being vague does not get your more leeway, it just increases the chances for misunderstanding.
Acknowledge performance
  Tell the person, the person’s boss, team members, peers.
View your people as allies not as adversaries
  Focus on common goals, not on individual agendas.
  Make people comfortable by encouraging brainstorming and creative thinking
Be a manager and a leader
  Deal with people as well as to deliverables, processes and systems.
  Create a sense of vision and excitement.
Notes: Don’t assume anything
  Take the time to find out the facts.

## Slide 59: Additional Readings
[IEEE Std 1058] Standard for Software Project Management Plans
Stanley E. Portny, Project Management for Dummies, Hungry Minds, 2001.
[Royce 1998], Software Project Management, Addison-Wesley, ISBN0-201-30958-0
[Boehm 1981] Barry Boehm, Software Engineering Economics, Prentice-Hall, 1981

## Slide 60: Summary
Dependency Graph:
  Identification of dependency relationships between activities identified in the WBS
Schedule
  Dependency graph decorated with time estimates for each activity
Critical path and slack time
Forward and Backward Path Analysis
PERT: Technique to analyze complex dependency graphs and schedules
Gantt Chart: Simple notation to visualize a schedule
Notes: Developing a project plan is is an art. Practice it!
Use project templates for yourself or your organization, build these templates iteratively
Start with a WBS : A dependency graph is the WBS plus dependencies.
A schedule is a dependency graph plus time estimates
The detailed planning horizon should not got beyond a 3 month time frame
Budget should not be specified before the work is clear:
  If the preplanning phase needs a budget, ask for a separate budget
Always be prepared for surprises

## Slide 61: Additional Slides

## Slide 62: What makes a Software Project successful?
User involvement 20
Support from upper management 15
Clear Business Objectives 15
Experienced Project Manager 15
Shorter project phases 10
Firm core requirements 5
Competent Staff 5
Proper Planning 5
Ownership 5
Other 5
100 %
Source: Standish Group 1998 (citation quite out of date)
Notes: Shorter project phases („Small milestones“) 10
Firm core requirements („basic requirements“) 5
http://www.standishgroup.com/sample_research/chaos1998.pdf

## Slide 63: Alternative Summary
Developing a project plan is an art. Practice it!
Use project templates for yourself or your organization, build these templates iteratively
Start with a WBS
Dependency graph = WBS + dependencies.
Schedule = dependency graph + time estimates
The detailed planning horizon should not go beyond a 3 month time frame
Budget should not be specified before the work is clear:
  If the preplanning phase needs a budget, ask for a separate budget
Always be prepared for surprises

## Slide 64: Sandwich Testing
Sandwich testing combines top-down and bottom-up testing
  Top-down testing tests the top layer incrementally with the components of the target layer
  Bottom-up testing tests the bottom layer incrementally with the components of the target layer
Modified sandwich testing is more thorough
  Individual layer tests
    Top layer test with stubs for target layer
    Target layer test with drivers and stubs replacing top and bottom layers
    Bottom layer test with a driver for the target layer
  Combined layer tests
    Top layer access the target layer
    Target layer accesses bottom layer

## Slide 65: West Buttress
Description: Route follows the winding Kahiltna Glacier to a large basin, where 2,000 feet of climbing yields the West Buttress.
Ascent to Denali Pass, from which the final ascent is made.
Rating Alaska Grade 2
Notes: This route has the reputation of being an easy climb,
but its steep grade, severe weather, and numerous crevasses demand caution and resp
Very dangerous is the denali pass, where many people have died on the descent after successfully clmbing
The summit. However, the route below 18,200-foot Denali Pass is not the deadliest place on McKinley.
That dishonor belongs to the Upper West Rib, on the southwest side of the mountain,
where 16 people have died since 1972, including 15 climbers who fell to their deaths.

## Slide 66: West Rib
Description Provides a direct route to the summit. The short, steep ascent requires only 3 miles of climbing, compared to 17 miles for the normal route on the West Buttress.
The route is steep (including short sections of up to 60-degree ice), but otherwise poses few serious technical difficulties.
Rating Alaska Grade 4
Notes: Picture: My own.
Description from : http://www.peakware.com/encyclopedia/peaks/routes/mckinley.htm
The West Rib was first climbed June 19, 1959 by the Jackson Hole climbers, Sinclair, Breitenbach, Corbet, and Buckingham.

## Slide 67: Cassin Ridge
Description This is a direct, 9,000-foot granite ridge up the South Face to McKinley's summit.
The route includes 40- to 65-degree snow and ice climbing, and up to 5.8 rock on several pitches below 16,400 feet.
Rating Alaska Grade 6
Notes: First ascent in 1961: An Italian party led by Ricardo Cassin is the first to summit McKinley via the Cassin Ridge.
The crux: The chimney after the Japanese Couloir.
Grade V.
Picture from From http://www.climbalaska.org/graphics/cassin2.html
Description from http://www.peakware.com/encyclopedia/peaks/routes/mckinley.htm

## Slide 68: Difficulty of Upper West Rib (Denali 6190m. Alaska)
ALLEVATION: 6,194 m
ROUTE:Upper West Rib, Alaska Grade III, 4000 m (13,000’) elevation gain, 49,6 Kilometer (31 miles)
Duration: 16-22+ days
Given a Grade IV, the Upper West Rib is considerably more difficult than the West Buttress due to the steeper terrain and awesome exposure. 30-45, ice and snow and mixed terrain characterize the Rib's upper face.
Summit day is a big push from 16,300' and requires a significant amount of fortitude and stamina.
Notes: Unique to Denali's rating system is an implied severity grade that makes any route a serious undertaking.
High altitude, extreme weather, and active glaciation combine to make Denali one of the most difficult and severe mountains in the world to climb.

## Slide 69: Cassin Ridge
The crux: The chimney after the Japanese Couloir.
Grade V
From http://www.climbalaska.org/graphics/cassin2.html
Notes: From http://www.climbalaska.org/graphics/cassin2.html

## Slide 70: Leadership and Team Work
From http://www.climbalaska.org/denali-rib.html
Successful expeditions are properly equipped, have the necessary skills, but most importantly they learn to become a strong team.
Leadership reflects the art of effective team building. From base camp to advanced base camp (ABC) your instructors teach classes and initiate you to the expectations of un-supported expedition life.
Above ABC all the way to the summit is the testing phase and a place to show signs of strength: tight camps, efficient travel techniques, and a positive attitude.
We expect you to stay organized, participate fully, have fun and support the goal of being on a strong and safe expedition.

## Slide 71: Leadership and Team Work 2
From http://www.climbalaska.org/denali-rib.html
Of primary importance is taking responsibility for monitoring yourself; you know best how you feel, how you sleep, how you recover each day.
As a team, we are able to help if someone is having a bad day and communicates this.
Every member must ultimately be a regular contributor for the expedition to be successful.
Not participating, or failing to meet the day-to-day demands may mean your departure from the expedition.
We expect you to have self-leadership skills and good expedition behavior (EB): be supportive, solution-oriented, hard working, patient, and take initiative and you will be rewarded with the climb of a lifetime