## Slide 1: Chapter 15, Software Life Cycle, Unified Process

## Slide 2: Outline of Today’s Lecture
Unified Process: An iterative process model
States of a software system developed with the Unified Process:
    Inception, Elaboration, Construction, Transition
Artifacts Sets:
    Management Set, Engineering Set
Workflows:
    Management, Environment, Requirements, Design, Implementation, Assessment, Deployment
Iterations
Managing iterations as software projects
Mistakes in managing iterations
Notes: Where are we? So far we have looked at the software lifecycle from a project’s point of view:
  “Hey, we have to do this, what activities should we use?”
Today, we look at an industrial strenght software lifecycle process from a business point of view
  Example: A company doing research and producing software commercially.
Purpose: Distinguish between research systems (“prototypes”) and real products
--------
States of a software project managed with the Unified Process:
    Inception, Elaboration, Construction, Transition
  Artifacts Sets:
    Management Set, Engineering Set
  Workflows:
    Management, Environment, Requirements, Design, Implementation, Assessment, Deployment
  Iterations

## Slide 3: Review of Definitions
Software life cycle:
  Set of activities and their relationships to each other to support the development of a software system
Software development methodology:
  A collection of techniques for building models - applied across the software life cycle

## Slide 4: Software Life Cycle Questions (Review)
Which activities should I select?
What are the dependencies between activities?
How should I schedule the activities?
Questions to ask:
  What is the problem?
  What is the solution?
  What are the mechanisms that best implement the solution?
  How is the solution constructed?
  Is the problem solved?
  Can the customer use the solution?
  How do we deal with changes that occur during the development? Are enhancements needed?

## Slide 5: Life Cycle Modeling
So far we have discussed the life cycle models
  Waterfall model
  V-model
  Spiral model
  Issue-based model
Today we will introduce another life cycle model
  Unified Software Process
Notes: The Unified Software Process is becoming a standard in industry.

## Slide 6: “Processes“ in the Unified Process
The term Process is overloaded in the Unified Process
Micro process: Policies & practices for building an artifact
  Focus: Intermediate baselines with adequate quality and functionality as economically and rapidly as practical
  Same as “Process” in the IEEE 1074 Standard
Macro process: A set of micro processes and the dependencies among them
  Focus: Production of a software system within cost, schedule and quality constraints
  Also called: Life cycle model
Meta process
  Focus: Organizational improvement, long-term strategies, and return on investment (ROI)
  Also called: Business process.
Notes: The term Process is overloaded in the Unified Process. It uses 3 types of processes:
Metaprocess (“Business process”). An organizations’s policies, procedures and practices for pursuing a software-intensive line of business.
  Focus: Organizational improvement, long-term strategies, and return on investment (ROI).
Macroprocess (“Lifecycle Model”). The set of processes in in a software lifecycle and dependencies among them.
  Focus: Producing a software system within cost, schedule and quality constraints.
Microprocess (“Process”). Policies, and practices for achieving an artifact of the software process.
  Focus: Intermediate baselines with adequate quality and adequate functionality as economically and rapidly as practical.

## Slide 7: The Unified Process
The Unified Process supports the following
  Evolution of project plans, requirements and software architecture with well-defined synchronization points
  Risk management
  Evolution of system capabilities through demonstrations of increasing functionality
It emphasizes the difference between engineering and production.
Notes: Historical note: The Unified Process is based on Ivar Jacobsen’s Objectory, a CASE Tool developed by Ericsson.
Emphasis on the difference between research/development and production
In the Unified Process this difference is modeled by introducing two major stages.
  Engineering Stage
  Production Stage
  This is shown on the next slide

## Slide 8: Difference: Engineering vs. Production
Engineering Stage
  Driven by less predictable but smaller teams, focusing on design and synthesis activities
Production Stage
  Driven by more predictable but larger teams, focusing on construction, test and deployment activities
Focus
Risk
Artifacts
Activities
Quality Assessment
Engineering Stage Emphasis
Technical feasibility, Schedule
Planning, Requirements, System Design Documents
Planning, Analysis, Design
Demonstration, Inspection
Production Stage Emphasis
Cost
Baselines, Releases
Implementation, Integration
Testing

## Slide 9: Phases in the Unified Process
The two stages of the Unified Process are decomposed into four distinct phases
Engineering stage
  Inception phase
  Elaboration phase
Production phase
  Construction phase
  Transition phase.
Notes: Note: Stages and phases are nothing else but arbitrary names of the states
(actually superstates and states) of a project.

## Slide 10: Transitioning from Engineering to Production
When the “engineering” of the system is complete, a decision must be made:
  Commit to production phase?
  Move to an operation with higher cost risk and inertia (i.e. bureaucracy)
Main questions:
  Are the system models and project plans stable enough?
  Have the risks been dealt with?
  Can we predict cost and schedule for the completion of the development for an acceptable range?
Notes: Most critical of the four phases
At the end of this phase, the “engineering” of the system is complete, and the organization faces the decision:
  - Shall we commit to the production phase?
  Shall we go from a low cost risk to an operation with higher cost risk and substantial inertia (i.e. bureaucracy).
  -------------
The main question is: Can the organization commit to a fixed-price construction phase?
----------------
  - Are the system models and project plans stable enough?
  - Have the risks been dealt with?
  - Can we predict cost and schedule for the completion of the development for an acceptable range?
    acceptable: 20-30 % of the predicted cost
    not acceptable: 100% above predicted cost

## Slide 11: States of a Software System in the UP
Elaboration
Inception
Construction
Transition
Transition from
engineering stage to
production stage.
Notes: Transitions between the four states are crucial events for project participants
(they are called stakeholders in the Unified Process) in particular the transition between
engineering and production.

## Slide 12: Inception Phase: Objectives
Establish the project scope
Identify the critical use cases and scenarios
Define acceptance criteria
Demonstrate at least one candidate software architecture
Estimate the cost and schedule for the project
Define and estimate potential risks.
Elaboration
Inception
Construction
Transition
Notes: Establish the project’s scope, in particular what is included and what is not included in the project to develop the system.
Define acceptance criteria for the software system
Identify the critical use cases of the system and primary scenarios of operation that will drive the major design trade-offs.
Demonstrate at least one candidate software architecture against some of the core scenarios
Estimate the cost and schedule for the entire project (including detailed estimates for the elaboration phase)
Define and estimate potential risks (sources of unpredictability)

## Slide 13: Inception Phase: Activities
Formulate the scope of the project
  Capture requirements
  Result: problem space and acceptance criteria are defined
Design the software architecture
  Evaluate design trade-offs, investigate solution space
  Result: Feasibility of at least one candidate architecture is explored, initial set of build vs. buy decisions
Plan and prepare a business case
  Evaluate alternatives for risks, staffing problems, plans.
Notes: Formulate the scope of the project. Capture requirements and operational concept in a repository that describes the user’s view of the requirements.
  Result: problem space and acceptance criteria are defined
Design the software architecture. Evaluate Design trade-offs, investigate solution space, check available solution space assets (existing components, technologies)
  Result: Feasibility of at least one candidate architecture, initial set of build vs. buy decisions so that cost, schedule and resource estimates can be derived.
  ====> Here ask this question: The Unified Process emphasizes the design of the software architecture very early. Why?
Plan and prepare a business case. Evaluate alternatives for risks, staffing problems, plans. Determine the infrastructure that is sufficient to support the development task.
Question: The Unified Process emphasizes the design of the software architecture very early. Why?

## Slide 14: Inception Phase: Evaluation Criteria
Do all stakeholders concur on the scope definition and cost and schedule estimates?
Are the requirements understood, are the critical use cases adequately modeled?
Is the software architecture understood?
Are cost, schedule estimates, priorities, risks and development processes credible?
Is there a prototype that helps in evaluating the criteria?
Notes: Apply the following questions to the results of the inception phase:

## Slide 15: Elaboration Phase: Objectives
Baseline the software architecture
  Establish a configuration management plan in which all changes are tracked and maintained
Baseline the problem statement
Base line the software project management plan for the construction phase
Demonstrate that the architecture supports the requirements at a reasonable cost in a reasonable time
Question: Why does the Unified process not recommend the establishment of a configuration management plan during the inception phase?
Elaboration
Inception
Construction
Transition

## Slide 16: Elaboration Phase: Activities
Elaborate the problem statement (“vision”) by working out the critical use cases that drive technical and managerial decisions.
Elaborate the infrastructure.
Tailor the software process for the construction stage, identify tools.
Establish intermediate milestones and evaluation criteria for these milestones.
Identify buy/build (“make/buy”) problems and make decisions.
Identify lessons learned from the inception phase to redesign the software architecture if necessary (“always necessary”:-)

## Slide 17: Elaboration Phase: Evaluation Criteria
Apply the following questions to the results of the inception phase:
  Is the problem statement stable?
  Is the architecture stable?
  Does the executable demonstration show that the major risk elements have been addressed and credibly resolved?
  Is the construction plan credible? By what claims is it backed up?
  Do all stakeholders (project participants) agree that the vision expressed in the problem can be met if the current plan is executed?
  Are actual resource expenditures versus planned expenditures so far acceptable?

## Slide 18: Construction Phase: Objectives
Minimize development costs by optimizing resources
Achieve adequate quality as rapidly as practical
Achieve useful version (alpha, beta, and other test releases) as soon as possible
Elaboration
Inception
Construction
Transition

## Slide 19: Construction Phase: Activities
Resource management, control and process optimization
Complete component development and testing against evaluation criteria
Assessment of product releases against acceptance criteria

## Slide 20: Construction Phase: Evaluation Criteria
Apply the following questions to the results of the construction phase:
  Is the product baseline mature enough to be deployed in the user community?
    Existing faults are not obstacles to do the release
  Is the product baseline stable enough to be deployed in the user community?
    Pending changes are not obstacles to do the release
  Are the stakeholders ready for the transition of the software system to the user community?
  Are actual resource expenditures versus planned expenditures so far acceptable?

## Slide 21: Transition Phase
The transition phase is entered when a baseline is mature
  A usable subset of the system has been built with acceptable quality levels and user documents
  It can be deployed to the user community
For some projects the transition phase means the starting point for another version of the software system
For other projects the transition phase means the complete delivery of the software system to a third party responsible for operation, maintenance and enhancement.
Elaboration
Inception
Construction
Transition

## Slide 22: Transition Phase: Objectives
Achieve independence of user (users can support themselves)
Deployment baseline is complete and consistent with the criteria in the project agreement
The final baseline can be built as rapidly and cost-effectively as possible.

## Slide 23: Transition Phase: Activities
Synchronization and integration of concurrent development increments into one consistent deployment baseline
Commercial packaging and production
Sales rollout kit development
Field personnel training
Test of deployment baseline against the acceptance criteria.

## Slide 24: Transition Phase: Evaluation Criteria
Is the user satisfied?
Are actual resource expenditures versus planned expenditures so far acceptable?

## Slide 25: Iterations in the Unified Process
Each of the four phases introduced so far (inception, elaboration, construction, transition) consists of one or more iterations
An iteration represents a set of activities for which there is a milestone (“well-defined intermediate event”)
  The scope and results of the iteration are captured via work products (called artifacts in the UP).

## Slide 26: Phase vs. Iteration
A phase creates a formal, stake-holder approved version of artifacts
  It leads to a “major milestone”
  Phase to phase transition:
    triggered by a significant business decision (not by the completion of a software development activity)
An iteration creates an informal, internally controlled version of artifacts
  It leads to a “minor milestone”
  Iteration to iteration transition:
    Triggered by a specific software development activity.
Notes: The transition from one phase to another phase is triggered by a significant business decision
and not by the completion of a specific software development activity.

## Slide 27: Artifact Sets in the Unified Process
Artifact: A work product in a uniform representation format (natural language, UML, Java, binary code,…)
Artifact set:
  A set of artifacts developed and reviewed as a single entity
The Unified Process distinguishes five artifact sets
  Management set
  Requirements set
  Design set
  Implementation set
  Deployment set
Also called the engineering set.
Notes: To make the development of complex systems manageable,
the Unified Process organizes work products produced during the development into artifacts sets.
The Unified Process distinguishes the following five sets

## Slide 28: Artifact Sets in the Unified Process
Requirements Set
1. Vision document
2. Requirements model(s)
Design Set
1. Design model(s)
2. Test model
3. Software architecture
Implementation Set
1. Source code baselines
2. Compile-time files
3. Component executables
Deployment
Set
1. Integrated pro- duct executable
2. Run-time files
3. User
documentation
Management Set
Planning Artifacts
1 Software Project Management Plan (SPMP)
2. Software Configuration Management Plan (SCMP)
3. Work breakdown structure
4. Business Case
5. Release specifications
Operational Artifacts
1. Release descriptions
2. Status assessments
3. Change Management database
4. Deployment documents
5. Environment.
Engineering Set

## Slide 29: Representation of Artifact Sets (1)
Management Set
  Goal: Capture plans, processes, objectives, acceptance criteria
  Notation: Ad hoc text, graphics, textual use cases.
Requirements set
  Goal: Capture problem in language of problem domain
  Notation: Structured text, UML models
Design set
  Goal: Capture the engineering blueprints
  Notation: Structured text, UML models.
Notes: Each artifact set has a different goal and uses different notations to capture the relevant artifacts.

## Slide 30: Rationale for Selection of Artifact Sets (2)
Implementation set
  Goal: Capture the building blocks of the solution domain in human-readable format
  Notation: Programming language
Deployment set
  Goal: Capture the solution in machine-readable format
  Notation: Machine language.
Notes: Each artifact set has a different goal and uses different notations to capture the relevant artifacts.

## Slide 31: Life-cycle Focus on Artifact Sets
Each artifact set is the predominant focus in one stage of the unified process.
Inception
Elaboration
Construction
Transition
Management
Set
Requirements
Set
Design Set
Implementation
Set
Deployment
Set

## Slide 32: Managing the Artifact Sets
Some artifacts need to be updated at each major milestone (after a phase)
Other artifacts must be updated at each minor milestone (after an iteration)
Artifact set roadmap
  Visualization of the updates of artifacts across the software life-cycle
The software project manager is responsible for managing the artifact set roadmap
  Artifact set roadmap: Focus on models
  Artifact set roadmap: Focus on documents.
Notes: In each phase of the life cycle, new artifacts (“work products”) are produced and
previously developed artifacts are updated to incorporate lessons learned and to capture further depth and breadth of the solution.

## Slide 33: Artifact Set Roadmap: Focus on Models
Inception
Elaboration
Construction
Transition
Management Set
Requirements Set
Design Set
Deployment Set
1. Vision
2. WBS
3. Schedule
4. Conf. Management
5. Project Agreement
6. Test cases
1. Analysis Model
1. System Design
2. Interface Specification
Implementation Set
1. Source code
2. Test cases
1. Alpha-Test
2. Beta-Test
Informal
Baseline
Notes: This is an artifact road map with the focus on the creatio of models.
Is this a good road map?

## Slide 34: Artifact Set Roadmap: Focus on Documents
Inception
Elaboration
Construction
Transition
Management Set
Requirements Set
Design Set
Deployment Set
1. Problem Statement
2. WBS
3. SPMP
4. SCMP
5. Project Agreement
6. Test plan
1. RAD
1. SDD
2. ODD
Implementation Set
1. Source code
2. Test cases
1. User Manual
2. Administrator Manual
Informal
Baseline

## Slide 35: Models vs. Documents
Many software project managers pay too much attention on the production of documents
Documentation-driven approach
  The production of the documents drives the milestones and deadlines
Model-driven approach
  The production of the models drive the milestones deadlines
Main goal of a software development project:
  Creation of models and construction of the software system
The purpose of documentation is to support this goal.
Notes: Many manager are tempted to pay too much attention on the production of documents.
Distinguish between the information inherent in the system models and the paper on which it is written (or the “bits on the screen”).
Extremely important: Distinguish between
  the information inherent in the system models (functional models, dynamic models, object models)
  and the paper on which it is written (or the “bits on the screen”).
The main goal of a software development project is the creation of models and the construction of the software system.
The purpose of documentation is to support this goal.

## Slide 36: Historical Reasons for Documentation-Driven Approach
People wanted to review information, but did not understand the language of the artifact
People wanted to review information, but did not have access to the tools to view the information
No rigorous engineering methods and languages were available for analysis and design models
  Therefore paper documents with ad hoc text were used
Conventional languages for implementation and deployment were highly cryptic
  A more human-readable format was needed
Managers needed “status”
  Documents seemed to be a good mechanism for demonstrating progress.
Notes: In the 60-90s a lot of time was spent on developing, formatting, reviewing, updating and distributing documents. Why?
  1) No rigorous engineering methods and languages was available for analysis and design models. Consequently, paper documents with ad hoc text were the default format.
  2) Conventional languages for implementation and deployment were highly cryptic. To present the details of software structure and behavior to other project participants (testers, managers, maintainers), a more human-readable format was needed.
  3) Software project progress needed to be assessed (managers, stakeholders needed “status”). Documents represented a tangible but misleading mechanism for demonstrating progress.
  4) People wanted to review information, but did not understand the language of the artifact.
  5) People wanted to review information, but did not have access to the tools to view the information.

## Slide 37: Artifact-Driven Approach
Provide templates for documents at the start of the project
Instantiate documents automatically from these templates
  Enrich them with modeling and artifact information generated during the project
Tools automatically generate documents from the models. Examples:
  Generation of analysis and design documents (Commercial CASE tools)
  Generation of the interface specification (Javadoc)
  Test case generation (J_Unit)
  Schedule generation (Microsoft Project).
Notes: Provide templates for documents at the start of the project.
Instantiate documents automatically from these templates
  Enriching them with modeling and artifact information generated during the project.
Tools automatically generate documents from the models. State of the art:
  Schedule generator (Microsoft Project)
  Automatic requirements document generator (Request)
  Automatic Interface specification generator (Javadoc)
  Automatic generation of analysis and design documents: Existing CASE Tools (Rationale Rose, Together-J)
  Automatic test case generation (J_Unit)

## Slide 38: Micro Processes in the Unified Process
The Unified Process distinguishes between macro and micro process:
  The macro process models the software lifecycle
  The micro process models activities that produce artifacts
The micro processes are also called workflows in the Unified Process.

## Slide 39: Workflows in the Unified Process
Management workflow
Environment workflow
Requirements workflow
Design workflow
Implementation workflow
Assessment workflow
Deployment workflow.
Notes: The Unified Process distinguishes seven workflows:

## Slide 40: Workflows in the Unified Process
Management workflow
  Planning the project (Problem statement, SPMP, SCMP, test plan)
Environment workflow
  Automation of process and maintenance environment. Setup of infrastructure (Communication, configuration management, ...)
Requirements workflow
  Analysis of application domain and creation of requirements artifacts (analysis model)
Design workflow
  Creation of solution and design artifacts (system design model, object design model).

## Slide 41: Workflows in the Unified Process (2)
Implementation workflow
  Implementation of solution, source code testing, maintenance of implementation and deployment artifacts (source code)
Assessment workflow
  Assess process and products (reviews, walkthroughs, inspections, testing…)
Deployment workflow
  Transition the software system to the end user.

## Slide 42: Workflows work across Phases
Workflows create artifacts (documents, models)
Workflows consist of one or more iterations per phase.
Implementation
Workflow
Management
Workflow
Requirements
Workflow
Design Workflow
Deployment
Workflow
Assessment
Workflow
Environment
Workflow
Inception
Elaboration
Construction
Transition

## Slide 43: Managing Projects in the Unified Process
How should we manage the construction of software systems with the Unified Process?
Approach
  Treat the development of a software system with the Unified Process as a set of several iterations
    Some of these can can be scheduled in parallel, others have to occur in sequence
  Define a single project for each iteration
  Establish work break down structures for each of the 7 workflows.

## Slide 44: Project Phases vs. Unified Process Phases
Every project has at least 5 states
  Conceiving: The idea is born
  Defining: A plan is developed
  Starting: Teams are formed
  Performing: The work is being done
  Closing: The project is finished.
Notes: Let’s review these briefly, to avoid confusion between the phases
in the Unified Process (Software Project Management) and
the generic phases of any project (Project Management).

## Slide 45: Phases of a Software Project
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
Notes: Let’s review the project phases briefly, to avoid confusion between the phases of a software system developed with
the Unified Process (Software Project Management) and
the phases of software project (Project Management).
Every project has at least 5 states
  Conception: The idea is born
  Definition: A plan is developed
  Starting: Teams are formed
  Performing: The work is being done
  Closing: The project is finished

## Slide 46: Project Phases vs. Unified Process Phases
Each iteration in the unified process phases
  Inception, Elaboration, Construction, Transition
should go through each of these 5 project phases!
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
Notes: Let’s review these briefly, to avoid confusion between the phases
in the Unified Process (Software Project Management) and
the generic phases of any project (Project Management).

## Slide 47: Unified Process Management Mistakes
Project manager skips the start phase
Project manager skips the definition and start phase
Project manager jumps straight to the steady state phase after joining the project late
Project manager cancels the termination phase.
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
X
X
X
X
X
X
X
Notes: These are general management mistakes.
For the unified process the penalty is even worse, because almost each iteration depends
on the previous one.

## Slide 48: Mistake: Skipping the Start Phase
Main reason: Time pressure
Reasons for start phase
  Inform stakeholders that the project has been approved and when work will start
  Confirm that stakeholders are able to support the project
  Reevaluate and reconfirm work packages with developers
  Explain your role as manager to stakeholders and developers.
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
X
Notes: Project Manager leaves out the start phase completely.
  The main reason is time pressure. Don’t let it happen to you.
The major reason to have a start phase is to confirm the participation of your project participants:
  Inform the stakeholders of your project that your project has been approved and when work will start
  Confirm that your stakeholders are still able to support your project
  Reconfirm work packages with developers
  Explain your role as manager to stakeholders and developers

## Slide 49: Mistake: Skipping Definition and Start Phase
Known territory argument
  “I have done this before, no need to waste time”
    Even though a project may be similar to an earlier one, some things are always different
Unknown territory argument
  “My project is different from anything I have ever done before, so what good is it to plan?”
    It is better to create a map if you are attempting to travel into unknown territory.
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
X
X
Notes: Project manager jumps directly from the conceive phase to the perform phase (Leaving out define and start phases).
Two reasons for that: Known territory, unknown territory
“I have done this before, no need to waste time”:
  Even though projects can be similar to ones done in the past, some things are always different. Examples: Working with different people, new type of equipment, new environment.
“My project is different from anything I have ever done before, so what good is it to plan?”
  You should try to look at a map if you are attempting to travel into unknown territory!

## Slide 50: Problem: Joining a Project Late
Joining a project late is not that uncommon
  Often the planning has been performed by another person, usually a high level manager, and you are asked to take the project over
  Or the project is in such a bad state, that the current project manager needs to be replaced
Reason to jump right into steady state phase
  “The plan has already been developed, so why should I go back to the conception and definition phases?”
Reasons to reevaluate the conception and definition phase:
  See if you can identify any issues that may have been overlooked
  Try to understand the rationale behind the plan and to decide if you feel the plan is achievable.
Notes: Joining a project late is not that uncommon. Often the planning has been performed by another person, usually a high level manager, and you are asked to take the project over.
Or the project is in such a bad state, that the current proejct manager has to be replaced.

## Slide 51: Mistake: No Termination Phase
Take the time to ensure that all tasks are completed or identified as open issues:
  Otherwise you never really know how successful your project was
Try to learn from your mistakes (“lessons learned”):
  If you don’t, you will make the the same mistakes again, and may even fail.
System Done
New Technology
Conception
do/FormulateIdea
do/Cost-BenefitAnalysis
do/FeasibilityStudy
do/Review
Definition
do/Problem Statement
do/Software Architecture
do/Software Plan
Start
do/Project Kickoff
do/Infrastructure Setup
do/Skill Identification
do/Team Formation
Steady State
do/Develop System
do/Controlling
do/Risk Management
do/Replanning
New Requirement
GoAhead
ScopeDefined
Termination
do/Client Acceptance
do/Delivery
do/Post Mortem
Teams assembled
Infrastructure done
X
Reasons for skipping or not completing the termination phase:
  You leave a project to move on right to the next one. (Because you are a successful manager:-)
  Scarce resources and short deadlines
  A new project is always more challenging than wrapping up an old one
Notes: Reasons for skipping or only partially completing the termination phase:
  You leave a project to move on right to the next one. This is the sign of a successful manager:-)
  Scarce resources and short deadlines
  A new project is always more challenging than wrapping up an old one.

## Slide 52: Summary
Unified Process: Iterative software lifecycle model
  Emphasis on early construction of a software architecture
  Emphasis on early demonstrations of the system
Definitions
  Phase: Status of the software system.
    4 phases: Inception, Elaboration, Construction, Transition
  Workflow: Mostly sequential activity that produces artifacts
    7 workflows: Management, environment, requirements, design, implementation, assessment, deployment.
    5 artifact sets: Management set, requirements set, design set, implementation set, deployment set
  Iteration: Repetition within a workflow.
Each unified process iteration is a software project.
Notes: The Unified Process is an iterative software lifecycle model with emphasis on the early construction of
a software architecture and early demonstrations of the system.
It consists of phases, workflows and iterations that produce artifacts.
  4 phases: Inception, Elaboration, Construction, Transition
  7 workflows: Management, environment, requirements, design, implementation, assessment, deployment.
  5 artifact sets: Management set, requirements set, design set, implementation set, deployment set

## Slide 53: Additional References
Walker Royce
  Software Project Management, Addison-Wesley, 1998.
Ivar Jacobsen, Grady Booch & James Rumbaugh
  The Unified Software Development Process, Addison Wesley, 1999.
Jim Arlow and Ila Neustadt
  UML and the Unified Process: Practical Object-Oriented Analysis and Design, Addison Wesley, 2002.
Philippe Kruchten
  Rational Unified Process, Addison-Wesley, 2000.
Notes: Note: The Rational Unified Process is a commercial product of the Unified Process.

## Slide 54: Additional Slides

## Slide 55: Component Based Software Development
Buy
  Commercial of the shelf components (COTS), reusable objects, …
Build
  Custom development, build everything from scratch,…
Comparision: Buy vs. Build

## Slide 56: Commercial Components (“Buy”)
Predictable license costs
Broadly used, mature technology
Available now
Dedicated support organization
Hardware/software independence (sometimes)
Rich in functionality
Frequent upgrades
Up-front license fees
Recurring maintenance fees
Dependency on vendor
Run-time efficiency sacrifices
Functionality constraints
Integration not always trivial
No control over upgrades and maintenance
Unnecessary features that consume extra resources
Often inadequate reliability and stability
Multiple-vendor incompatibilities.

## Slide 57: Custom Components (“Build”)
Complete change freedom
Smaller, often simpler implementations
Often better performance
Control of development and enhancement
Expensive, unpredictable development
Unpredictable availability date
Undefined maintenance model
Often immature and fragile
Single-platform dependency
Drain on expert resources.

## Slide 58: Model of the Unified Process (Analysis)
Inputs:
  Problem Statement
Functional Requirements:
  Top level use case: Develop software system that implements the problem statement.
Outputs:
  Requirements analysis document
  Software project management plan
  Software configuration management plan
  System design document
  Object design document
  Test plan and test cases
  Source code
  User manual and administrator manual

## Slide 59: Model of the Unified Process: System Design
Design Goals:
  High performance, dependability, low cost, maintainability, usability
Subsystems:
  The workflows Management, Environment, Requirements, Design, Implementation, Assessment, Deployment
Hardware/Software mapping:
  Each subsystem is running on its own node.
Concurrency:
  The threads can run concurrently.
Global control flow:
  Event-driven. The subsystems communicate via events. Typical events are: „Requirement has changed“, „Review comments available“, „Time has expired“)
Notes: Let’s model the system design in the unified process

## Slide 60: Model of the Unified Process: System Design (ctd)
Persistent Data:
  Vision, Process Model, Configuration Items, Analysis Model, System Design Model, Object Design Model, Communication data.
Access control:
  Stakeholders (End users, managers, customers, developers, …) have access to the persistent data with access rights defined dynamically by environment workflow.
Boundary Conditions
  Startup of workflows: All workflows start simultaneously
  Steady state of workflows: Workflows wake up on an event, process the event, and go to sleep afterwards.
  Terminal conditions of workflows: A risk has occurred that cannot be dealt with

## Slide 61: Lifecycle Improvement
There are 3 possibilities to improve a multi-step process
  Quality improvement: We take an n-step process and improve the efficiency of each step
    Example: TQM (Total Quality Management)
  Overhead reduction: We take an n-step process and eliminate some of the steps
    Example: Extreme Programming
  Concurrency: We take an n-step process and parallelize some of the seps or use more concurrency in the resources being used
    Example: Unified Process.